# Cochrane Training: progress update

Prepared by Steve McDonald, TWG Co-Convenor, and Miranda Cumpston, Training Co-ordinator

on behalf of the Training Working Group (see page 4 for members), 18th September 2011

Purpose

To update the Steering Group on the progress towards achieving the project deliverables as outlined in the workplan for the first phase of Cochrane Training; to highlight any major concerns or delays, including any resource implications.

Urgency

Low (for information only)

Access

Open

Background

At its meeting in Keystone, the Steering Group approved the detailed workplan presented by the Training Working Group together with the funding request of £192,000 GBP for the first phase (to March 2012). The workplan contains 20 discrete projects that were selected on the basis of a prioritisation exercise that culminated with the meeting of the Training Working Group in Oxford April 2010. The projects are grouped into four main areas: 1) authoring reviews, 2) editing reviews, 3) managing and supporting reviews, and 4) training co-ordination. Collectively, the projects contribute to achieving the overall goal of Cochrane Training which is ‘that everyone who contributes to preparing Cochrane reviews, in whatever capacity, has access to timely, comprehensive and high quality training and support, sufficient to enable those with minimum competencies to fulfil the requirements of their role’.

Overall, although there have been delays to the start of several projects, we are pleased with the progress made in developing author training materials (where the majority of funding has so far been targeted). For the working groups involved in revising or creating mentoring and induction programmes, the changes within the Collaboration (e.g. new structures, Archie workflows, Central Register of Studies) have resulted in delays. The projects aimed at training and supporting editors and editorial functions, which are not currently linked to funded projects, will be the focus of the next phase of Cochrane Training and will be developed in collaboration with the Cochrane Editorial Unit.

This paper summarises progress since Split (building on progress since Keystone) and highlights major concerns or delays, current issues and resource implications. Detailed individual project progress reports are included as an Appendix.

Proposals and discussion

- Miranda Cumpston was appointed Training Co-ordinator and started in the role in August 2011. This appointment will allow progress to be made on several of the individual projects that had been delayed, in particular the formation of the Cochrane Trainers’ Network, the implementation of a webinar programme, and the further development of the Cochrane Training website.

- Good progress has been made in developing resources to support and train authors (of intervention reviews). Three new modules as part of the second phase of the online learning resources project will be ready by the end of 2011 and the remaining four modules ready by mid-2012. In parallel with developing the modules we are exploring the opportunities for marketing this as a learning resource to organisations outside Cochrane and will involve the relevant groups within the Collaboration to bring forward proposals.

- Approval of the remaining standard author training materials (Phase 1) is expected by Madrid and follows a thorough review by the relevant Methods Groups; this represents a suite of training materials that covers all the basics steps in completing a Cochrane review. Attention has now turned to promoting their use through the Trainers’ Network and creating translated versions. The next phase of this project will involve supplementing the core materials with additional workshop-based interactive exercises, and liaising with trainers to identify priority topics for Phase 2.

- The TWG has drafted a policy on how the standard author training materials can be used and amended, and how they should be acknowledged. This will be communicated to members of the Trainers’ Network and through the Training website.

- There are delays to the project to provide online access to training materials for Cochrane DTA reviews, largely due to time constraints and the commitments of the small group involved in drafting and scripting the presentations. However, the annual DTA workshop for authors and entity staff is taking place in Amsterdam at the end of September 2011 and a full program of DTA workshops will be run at the Colloquium.

- As part of the package of training in support of DTA reviews, alternating annual workshops in statistical methods and information retrieval methods were scheduled from 2011. These training events have been put on hold because further training for these groups is not felt to be needed at this time.

- The initial focus of Cochrane Training has deliberately been centred around authors and thus the provision of training for editors has been minimal. The next phase of the Cochrane Training workplan will focus much more on editing (in close collaboration with CEU) and will include requests for funded projects. It’s likely that the MECIR work will have a major impact on both the content and structure of editor training.

- One area in which some progress has been made is with Feedback Editors. As part of the CEU’s broader efforts to enhance feedback, there are proposals to convene a small group of Feedback Editors to help develop resources and an induction package.

- The Applicability and Recommendations Methods Group hosted the annual training event for methodologists (and those taking responsibility for the implementation of methodology) within Review Groups and Centres. The purpose of the event was to build an international network of experts in Summary of Findings Tables and GRADE who will support authors.

- In relation to the mentoring and induction schemes for entity staff, and in particular MEs, a delay has been requested in the implementation of the planned new models while several issues are resolved, including the role of IMS Support; the role of the CEU in co-ordinating these programs; the impact of major projects such as workflows and the CRS; and ensuring consistency between the models. (Details are provided in a separate paper to the Steering Group prepared by Sonja Henderson.) It is likely that all three models (MEs, TSCs and Fields) will be delayed until mid-2012, although background preparatory work continues, including the identification of training needs, induction checklists and role descriptions for the TSC and Field mentoring schemes.

- Before the Colloquium, the TWG co-convenors and Training Co-ordinator are meeting in Oxford to begin planning for the next phase of Cochrane Training and to draft a formal workplan for the Training Co-ordinator for Nov 2011 to Oct 2012 (that will be put before the TWG for approval).

- During other meetings in Oxford, we are meeting with the Consumer Co-ordinator to discuss training and support initiatives for consumer contributors to the Collaboration, which were omitted from the first phase of Cochrane Training.

- We are mindful that the proposals before the Steering Group to restructure the executive functions within The Cochrane Collaboration place Training and Education under the responsibility of the Cochrane Editorial Unit. We have meetings organised with David Tovey to discuss future governance and reporting arrangements for Cochrane Training (encompassing the Training Working Group, Training Co-ordinator and training projects).

- At the Colloquium, the Training Co-ordinator will be available to meet with delegates at the Cochrane Exchange and we plan to produce a Cochrane Training news sheet.

Resource implications

Because of delays to several of the funded projects (the appointment of the Training Co-ordinator, the mentoring and induction programmes, and the DTA online training materials) we estimate that Cochrane Training will be under budget by c. £74K (of the £192K originally approved) for the period October 2010 to March 2012. The budget estimated for Cochrane Training for April 2012 onwards of £103K is accurate for the projects covered, however, we anticipate requesting additional resources to cover training initiatives aimed at editors and consumers. These will be outlined in the Phase 2 workplan to be submitted at the 2012 mid-year meeting.

| Project funding to March 2012 | Approved | Actual at Sep 2011 | Est. by Mar 2012 |
| --- | --- | --- | --- |
| Online Learning Resources | £50,000 | £50,000 | - |
| Screen capture videos for RevMan | £1,000 | - | £1,000 |
| Online access to DTA training materials | £13,250 | - | - |
| Annual workshop for DTA reviews | £6,500 | - | £3,000 |
| ME Induction and Mentoring Programme | £5,785 | £3,162 | £2,623 |
| TSC Induction and Mentoring Programme | £9,125 | - | £6,000 |
| Fields Induction and Mentoring Programme | £4,350 | - | £2,250 |
| Editorial Resources Committee | £10,250 | - | £3,500 |
| Methods Groups’ annual training event | £20,000 | £13,130 | - |
| Statistical methods for DTA reviews | £2,000 | - | - |
| Information retrieval for DTA reviews | £2,000 | - | - |
| Cochrane Training Co-ordinator | £67,500 | - | £33,333 |
| TOTALS | £191,760 | £66,292 | £51,706 |

Impact statement

Not applicable.

Decision required

None.

Membership of the Training Working Group (Sep 2011)

At our meeting in Keystone we agreed to extend membership of the TWG to include representatives of all groups and entities which have projects that are part of Cochrane Training.

| Co-convenor | Steve McDonald |
| --- | --- |
| Co-convenor | Phil Wiffen |
| Training Co-ordinator | Miranda Cumpston |
| Managing Editors’ Executive | Sally Bell-Syer |
| Co-ordinating Editors’ Executive and MARS Working Group | Rachel Churchill |
| CCSG Author representative | Donna Gillies |
| Cochrane Handbook, MARS Working Group and Methods Exec | Julian Higgins |
| Methods Co-ordinator | Jackie Chandler |
| Fields’ Executive | Susan Wieland |
| TSCs’ Executive | Lynn Hampson |
| Consumer Co-ordinator | Catherine McIlwain |
| Cochrane IMS | Olga Ahtirschi |
| Representing authors from LMICs | Malinee Laopaiboon |
| Cochrane Web Team | Chris Mavergames |
| Copy Edit Support | Nancy Owens |
| Representing LOTE authors | Marta Roqué |
| Expertise in eLearning (stepped down August 2011) | Adrienne Stevens |
| Cochrane Editorial Unit | Rachel Marshall |
| Editor representative | Andrea Nelson |
| DTA Working Group | Rob Scholten |

Summary of projects (September 2011)

| Authoring reviews | Description / output | Lead | Timeline | Status |
| --- | --- | --- | --- | --- |
| [$] Online Learning Resources | Development of eight new modules and an update to existing online learning resources modules | UKCC | Dec-11 | G |
| Standard author training materials | Next phase of standard training materials for Cochrane authors | ACC | Mar-12 | A |
| ‘Cochrane Live’ webinar programme | eLearning via webinars for authors, editors and staff of entities | TWG | Ongoing | A |
| Screen capture videos for common tasks in RevMan | Series of ‘how to’ screen capture videos that demonstrate some of the commonest tasks in RevMan | UKCC, ACC | Dec-11 | A |
| [$] Online access to training materials for DTA reviews | Online access to training materials for Cochrane authors and others (editors, entity staff) preparing a DTA review | DTA WG | Jun-11 | A |
| [$] Annual workshop on developing a DTA review | Annual face-to-face training for Cochrane authors and other interested parties (editors, entity staff) | DTA WG | Sep-11 | G |

| Editing reviews |  |  |  |  |
| --- | --- | --- | --- | --- |
| Editor training and induction | Materials for training new and existing Cochrane editors to effectively contribute to the work of CRGs | UKCC | Mar-12 | A |
| Peer review skills training | Materials to facilitate peer reviewing skills to improve the quality of feedback on Cochrane reviews and protocols | UKCC | May-12 | A |
| Copy Edit Support: training for copy editors | Structured training program to ensure that all Cochrane copy editors are working to a consistent level of quality | CES, CEU, Wiley | Ongoing | G |
| Publication ethics package | Materials covering issues such as authorship, plagiarism, conflicts of interest, conflict resolution and co-publication | UKCC | Jun-11 | A |

| Managing and supporting reviews |  |  |  |  |
| --- | --- | --- | --- | --- |
| [$] ME Induction and Mentoring Programme | Ongoing mentoring programme for new MEs, comprising a Mentoring Co-ordinator and four regional mentors | MEs Exec | Mar-12 | A |
| [$] TSC Induction and Mentoring Programme | Standard induction documents and a mentoring programme for new TSCs | TSCs Exec | Mar-12 | A |
| [$] Fields Induction and Mentoring Programme | Standard induction documents and a mentoring program for new Field Administrators and/or Co-ordinators | Fields Exec | Mar-12 | A |
| IMS: structured training and support pilot for non-CRGs | Structured training and support in the use of IMS to Centres, Fields and Methods Groups | IMS | Jun-11 | G |
| [$] Editorial Resources Committee | Dedicated research assistant support to the Editorial Resources Committee | ACC | Mar-12 | A |
| [$] Annual training for methodologists | Annual face-to-face training event to be hosted by a Methods Group | Methods Board | Ongoing | G |
| [$] Training in statistical methods for DTA reviews | Biennial face-to-face training every two years for Cochrane statisticians and methodologists | DTA WG | Jul-11 | A |
| [$] Training in info. retrieval methods for DTA reviews | Biennial face-to-face training every two years for Cochrane TSCs in the various aspects of study identification | DTA WG | Jul-12 | A |

| Training co-ordination |  |  |  |  |
| --- | --- | --- | --- | --- |
| [$] Cochrane Training Co-ordinator | Establish the position of Training Co-ordinator | TWG |  | G |
| Cochrane Trainers’ Network | Network of people actively involved in developing training materials and/or providing training | TWG | Ongoing | G |

[$]  = funded ‘Cochrane Training’ project

Status definitions (as used by CEU): GREEN ‘everything fine and going according to plan’; AMBER ‘delayed or minor problem encountered’; RED ‘major problem, project stopped’

APPENDIX: individual project progress reports

Notes: projects follow the order in the original proposal (i.e. grouped by authoring reviews, editing reviews, managing/supporting reviews, and training co-ordination). The interim steps included in the tables below are as stated in the original proposal.

| Title | Online Learning Resources (Phase 2) |
| --- | --- |
| Description or purpose | Development of seven new modules and an update to existing online learning modules |
| Start–finish date | July 2010 to December 2011 (Following the establishment of an agreement between The Cochrane Collaboration and University of Portsmouth, the project timescale has been revised to December 2010 to July 2012) |
| Interim steps | - Preparation of the following modules (timelines amended Sep 2011): - Risk of bias (to be delivered end Sep 2011) - Types of data (early 2012) - Analysing data (late 2011) - Writing and presenting results (late 2011) - Interpreting results and drawing conclusions (early 2012) - Evaluating a systematic review (mid 2012) - Economics methods (in partnership with the Campbell and Cochrane Economics Methods Group) (late 2011) - An evaluation exercise to determine the opportunities to raise income from the modules outside the Cochrane community |
| Progress since Keystone | - Discussions underway with Web Team and an independent IT consultant to reconfigure existing modules to update their appearance on the website and to streamline switching between modules for authors - Risk of bias module: final stages, being checked by Bias Methods Group and amendments being made - Types of data module: content almost ready - Analysing data module: in progress - Economics methods module: content currently circulated for comment - Evaluation exercise: investigating organisation appointed, work in progress - Contract between the Collaboration and UKCC/UoP has yet to be signed |
| Progress since Split | - Risk of bias module: content has been checked by Bias Methods Group, amendments made, and final programming is being completed - Types of data module: content almost ready (storyboard format), needs to be reviewed by methodologist - Analysing data module: preliminary content has been programmed with initial round of peer review feedback received; requires amendments prior to methodological sign-off - Economics methods module: content has been circulated for methodological comment; module has been programmed however requires further input from a pedagogic viewpoint to make it more accessible - Writing and presenting results module: one section of content (Lay Summaries) has been developed and received review, currently being programmed - Interpreting results and drawing conclusions module: content is being developed (storyboard format), requires methodological comment - Evaluation exercise: independent market research organisation has undertaken investigation into marketing opportunities and produced report; potential partner organisations for dissemination outside The Cochrane Collaboration have been identified and require further investigation - Contract between the Collaboration and UKCC/UoP has been signed and the full payment (£50K) made |

| Title | Standard author training materials (Phase 2) |
| --- | --- |
| Description or purpose | Next phase of standard training materials for Cochrane authors |
| Start–finish date | November 2010 to March 2012 |
| Interim steps | - Dissemination of materials developed during Phase 1 through a new Cochrane Trainers’ Network - Consultation with trainers, Methods Groups and Review Groups to identify priority areas for development of new training materials - Identify collaborators to develop content for advanced training topics - Consultation with MARS to identify exemplar reviews and worked examples to supplement existing materials (January 2011) - Agreed work plan for Phase 2 (February 2011) - Receipt of feedback on materials developed during Phase 1 as implementation proceeds |
| Progress since Keystone | - Commencement delayed, due to a delay in the completion and approval of the Phase 1 materials, and pending the appointment of the Training Co-ordinator and the establishment of the Trainers’ Network - Initial dissemination of the Phase 1 materials has begun via the new Cochrane Training website, and receipt of feedback is ongoing - Pilot project to translate into other languages (Korean) is underway - Consultation around the development of new materials and the development of the workplan expected to be completed by June 2011, with the aim to produce a set of prioritised materials by March 2012 |
| Progress since Split | - Approval of the Phase 1 materials is almost complete following thorough review by the relevant Methods Groups; it is anticipated that all materials will be approved by the Methods Board at or before the Madrid Colloquium - Materials are made available via the Cochrane Training website as they are approved - Agreement has been reached by the TWG on the policy for use, amendment and acknowledgement of the materials - Discussions between the Training Co-ordinator and some Centre trainers have begun, covering the incorporation of standard materials into regional training programs and identifying priority materials for Phase II, including additional interactive exercises to support the Phase 1 materials and advanced topics - Trainers and others will be able to view the Phase 1 materials and discuss their use with the Training Co-ordinator at the Cochrane Exchange at the Colloquium - Consultation around the development of new materials and the development of the workplan is expected to be completed by January 2012, with the aim to produce a set of prioritised materials by October 2012 |

| Title | ‘Cochrane Live’: webinar programme |
| --- | --- |
| Description or purpose | eLearning via webinars for authors, editors and staff of entities |
| Start–finish date | Ongoing |
| Interim steps | - Implementation of the webinar programme (i.e. logistics, content) in consultation with the proposed Training Co-ordinator and TWG - Completion of standard operating procedures documents - Establish regional co-ordinators (linked to the Trainers’ Network) - Ensure access to the appropriate webinar platform (e.g. Elluminate) and purchase software to convert recordings (e.g. QuickTime Pro) |
| Progress since Keystone | - Drafted guidelines, including technical notes, on how to plan webinars - Purchased licence to Elluminate - Webinar series for Managing Editors and RevMan trainers run by IMS Team scheduled for February/March 2011 to coincide with the release of RevMan 5.1 - Completion of standard operating procedures and implementation of a comprehensive webinar series are delayed pending the appointment of the Training Co-ordinator and the establishment of the Trainers’ Network |
| Progress since Split | - Licence for Blackboard Collaborate (formerly Elluminate) has been renewed, and is now available for Collaboration-wide use (managed by the Training Co-ordinator). Trainers and others will be able to view the software and discuss its use with the Training Co-ordinator at the Cochrane Exchange in Madrid - Regional co-ordinators will be identified and training offered in conducting webinars by December 2011 - Webinar series are planned for late 2011/early 2012 to support the rollout of mandatory workflows and the CRS, and are under consideration to support other major projects such as MECIR |

| Title | Screen capture videos for common tasks in RevMan |
| --- | --- |
| Description or purpose | Series of ‘how to’ screen capture videos that demonstrate some of the commonest tasks in RevMan |
| Start–finish date | January to December 2011 |
| Interim steps | - Familiarity with software, probably Captivate - Agree priorities with IMS, MEs, Centre/trainers |
| Progress since Keystone | - First video started but halted pending the delayed release of RevMan 5.1 - Delay in agreeing priority list of ‘how to’ videos pending the appointment of the Training Co-ordinator |
| Progress since Split | - Start delayed; expect to begin creating videos in early 2012 following consultation with relevant entity Executives to agree priorities |

| Title | Online access to training materials for developing a Cochrane DTA review |
| --- | --- |
| Description or purpose | Online access to training materials for Cochrane authors and others (editors, entity staff) preparing a DTA review |
| Start–finish date | January to June 2011 |
| Interim steps | - Revise existing DTA Power Point presentations - Develop scripts based on existing recordings of previous workshops - Produce eight modules (PPT slide show with spoken text and an interactive test) - Publish presentations on website - Pilot test each module and revise, if necessary - Launch programme on website |
| Progress since Keystone | - Content of each module is being discussed, but not agreed yet - Delay is likely to push timeline out until December 2011 |
| Progress since Split | - Project still not started officially due to time constraints and too many commitments of the (currently too small set of) involved people; a call for other DTA people who might be interested to develop (parts of) a module will be sent to the broader DTA network - Presentation on searching for DTA studies will shortly be submitted to the Screening and Diagnostic Tests Methods Group and Information Retrieval Methods Group for approval - Delay is likely to push timeline out until June 2012 |
| Title | Annual workshop on developing a Cochrane DTA Review |
| Description or purpose | Regular face-to-face training opportunities for Cochrane authors and other interested parties (editors, entity staff) in the various aspects of preparing a DTA review |
| Start–finish date | September 2011 |
| Interim steps | - Revise and update existing DTA workshop materials - Advertise, run and evaluate workshop |
| Progress since Keystone | - Workshop will be June or September 2011, depending on the availability of rooms (to be finalised before CCSG meeting in Split) |
| Progress since Split | - Workshop for authors will be held from 29-30 September in Amsterdam - 32 registrations (as at 12 September) |

| Title | Editor training and induction |
| --- | --- |
| Description or purpose | Materials for training new and existing Cochrane editors to effectively contribute to the work of CRGs |
| Start–finish date | January 2011 to March 2012 |
| Interim steps | - Capture existing materials used within Cochrane |
| Progress since Keystone | - Not yet started |
| Progress since Split | - Consideration of how best to address the training and support needs of editors will be addressed in the second phase of Cochrane Training and will take account of ongoing initiatives, such as MECIR and the proposed peer support networks for methods - Discussions with CEU about training and induction for Feedback Editors; CEU is planning to recruit a small group of Feedback Editors to help with the following proposals: - Role description for Feedback Editors - Guidelines and expectations (e.g. guiding principles, ethics, timelines, etc.) - Induction package (to include practicalities, examples of good practice, etc.) |

| Title | Peer review skills training |
| --- | --- |
| Description or purpose | Materials to facilitate peer reviewing skills to improve the quality of feedback on Cochrane reviews and protocols |
| Start–finish date | June 2011 to May 2012 |
| Interim steps | - Identify key issues in peer review in consultation with MEs and CEU - Identify existing materials - Develop materials as required |
| Progress since Keystone | - Not scheduled to start on this until mid-2011 |
| Progress since Split | - Not yet started - Made contact with a group of Canadian dieticians (supported by Cochrane Canada) about the development of a peer review module designed to help dieticians learn how to peer review Cochrane reviews |

| Title | Copy Edit Support: training for copy editors (ongoing) |
| --- | --- |
| Description or purpose | Structured training program to ensure that all Cochrane copy editors are working to a consistent level of quality |
| Start–finish date | Ongoing |
| Interim steps | - Develop new and update existing training materials for more widespread implementation - Present and solicit feedback from potential users - Explore use of eLearning tools to facilitate training and support - Ensure integration with existing CRG editorial procedures |
| Progress since Keystone | - Final stages of updating the Copy Editing Checklist to work with RevMan 5.1 and with other checklists being developed or used in CRG editorial processes; when completed, this will be submitted to ERC for approval and adoption across CRGs - Approved checklist will serve as the basis for applying a consistent copy editing standard across all CRGs (whether copy editors are working through CES or as an accredited copy editor within a CRGs) - Once the new checklist is implemented it will be used to assess whether quality standards are being achieved, and to develop and target training accordingly |
| Progress since Split | - At their meetings in Split, the formal CEU proposal to adopt universal copy editing of published reviews, and to centralise accreditation of copy editors, was approved by the CRGs - An updated assessment exercise is now available for accreditation of CRG copy editors; this will be rolled out in four phases over the next year. Due to resource constraints, CES does not currently propose to provide training to individual CRG copy editors, although training continues to be available to CES copy editors serving all CRGS. CES will ensure regular dissemination of updates to the Style Guide and other relevant policy to all copy editors, and a list of available external training resources is available on the CES website. - Draft copy editing checklists for use by all CRGs and copy editors have been generated, and are currently in the final stages of consultation and approval by the ERC |

| Title | Publication ethics package |
| --- | --- |
| Description or purpose | Materials covering issues such as authorship, plagiarism, conflicts of interest, conflict resolution and co-publication |
| Start–finish date | July 2010 to June 2011 |
| Interim steps | - Map existing guidance and documentation; identify potential gaps - Liaise with entity executives to identify priority topics - Develop a series of journal articles (including translation in other languages) - Prepare Handbook chapter |
| Progress since Keystone | - Final draft of first in series of journal articles almost complete; needs to be shared with CEU then published in Chinese Journal of EBM and translated - Delays to the remaining parts of the projects |
| Progress since Split | - Article by Wager and Wiffen on ‘Ethical issues in preparing and publishing systematic reviews’ now published in Chinese Journal of EBM and is being highly accessed within China - Work about to start on a related chapter for the Cochrane Handbook |

| Title | ME Induction and Mentoring Programme |
| --- | --- |
| Description or purpose | Ongoing mentoring programme for new MEs, comprising a Mentoring Co-ordinator and four regional mentors |
| Start–finish date | October 2010 to April 2012 (ongoing, subject to evaluation) |
| Interim steps | - Relevant documents updated (e.g. training guidelines, induction checklist, needs assessment form, evaluation questionnaires) - Role description for Mentoring Co-ordinator - Process for selecting new mentors - Documentation stored on Archie and training website (as appropriate) |
| Progress since Keystone | - MEs Exec is drafting proposals for a new model of ME Training (paper tabled for discussion at the Split meetings); paper addresses issues of when and by whom the evaluation will be done to inform the new model - Vicki Pennick is stepping down as Mentoring Co-ordinator in June and will be replaced by Narelle Willis until March 2012 |
| Progress since Split | - At the Split meetings, a new model for ME mentoring and induction was approved, designed to merge with and incorporate the IMS Support program; this program was intended to commence at the expiry of funding for the current programs (April 2012) - An induction checklist has been finalised in consultation with the MEs - There is now agreement that additional consideration is required before the new model can be adopted; issues to be resolved include the role of IMS Support for non-CRGs, role of CEU in co-ordinating these programs, impact of major projects such as workflows and the CRS, and ensuring consistency between the models - It is proposed that the model to be adopted be reviewed in consultation with the MEs, TSCs, IMS, CEU and Fields; the review will be co-ordinated by the Training Co-ordinator - A proposal for interim funding for the existing mentoring and IMS Support programs has been submitted in a separate paper to the Steering Group; a revised model for mentoring in the Collaboration will be submitted to the Steering Group at the mid-year meeting in Paris in 2012 |

| Title | TSC Induction and Mentoring Programme |
| --- | --- |
| Description or purpose | Standard induction documents and a mentoring programme for new TSCs |
| Start–finish date | November 2010 – April 2012 |
| Interim steps | - Convene an Induction Working Party - Survey TSCs on their experiences of starting in the role (if reqd.) - Update generic TSC position description as necessary - Develop training guidelines and induction checklist - Select mentors - Develop needs assessment form and post-visit questionnaires - Pilot mentoring programme - Role description for Mentoring Co-ordinator (if programme continues) |
| Progress since Keystone | - Working party convened (Lynn Hampson, Vittoria Lutje, Karen Hovhannisyan and Ruth Foxlee) - Agreed that surveying TSCs is not necessary; instead will make use of the needs assessment exercise from April 2010 - Suggested minor changes to the generic TSC position description - Agreed that guidelines for mentors will be based around the headings in the position description - Start of the 12-month mentoring pilot (due for April 2011) put back while work starts in earnest on the induction checklist and training guidelines |
| Progress since Split | - Induction checklist almost finalised (requires additional IMS items); will be sent to all TSCs for discussion in Madrid and then final approval by TSCs Exec - Training guidelines part developed; extra IMS items around workflows plus CRS - The imminent roll-out of the CRS has the potential to change TSC working practices and will need to be integrated within existing induction documentation - Given the proposed review of the mentoring schemes outlined above, including the implications for IMS Support of TSCs and the benefits of consistency and co-ordination of mentoring models, the TSC mentoring pilot will be delayed pending the outcome of the review and is unlikely to be ready before April 2012 |

| Title | Fields Induction and Mentoring Programme |
| --- | --- |
| Description or purpose | Standard induction documents and a mentoring program for new Field Administrators and/or Co-ordinators |
| Start–finish date | October 2010 to March 2012 |
| Interim steps | - Convene an Induction Working Party - Survey Field Administrators and Co-ordinators on their experiences of starting in the role - Update generic Field Administrator position description as necessary - Develop training guidelines and induction checklist - Select mentors - Pilot mentoring program - Role description for Mentoring Co-ordinator (if program continues) |
| Progress since Keystone | - Project partly on-hold while the new governance arrangements and expectations for Fields (e.g. core functions, monitoring requirements) are worked through by the Fields Exec - Fields Exec is currently revising job descriptions and titles for Field staff, as part of rewriting the Field section in the Cochrane Policy Manual - Start has been made on drafting the training materials, but these cannot be finalised until the responsibilities of Field staff are agreed; when the fundamentals are in place and the training requirements are clear, the activities outlined in the original plan will proceed - Start of the 12-month mentoring pilot (due for April 2011) likely to delayed by 3-4 months |
| Progress since Split | - Core functions of Fields have been revised and new titles for Field staff (Director and Co-ordinator) have been agreed and implemented - Generic position descriptions are being revised as part of the revisions to the Fields section of the Policy Manual - Draft training guidelines based on the new core functions will be trialled in two upcoming training events: - A day’s induction training for the Co-ordinator and Director of Justice Health Field (to be run by the CAM Field) - Training and support workshop at the Colloquium on ‘The complex and challenging mandate of Cochrane Fields’ for existing staff of Fields - Training efforts seen as important part of Fields Exec work but a decision about the scope and nature of any mentoring scheme will be reconsidered in light of recent changes to the functions of Fields, the upcoming training events, and the proposed review of the mentoring schemes outlined above |

| Title | IMS: structured training and support pilot for non-CRGs |
| --- | --- |
| Description or purpose | Structured training and support in the use of IMS to Centres, Fields and Methods Groups |
| Start–finish date | September 2010 to June 2011 (ongoing pending successful pilot) |
| Interim steps | - Relevant documents, materials drafted and feedback sought - Announcement of pilot to non-CRG entities - Setting up webinar series (from Nov 2010) - Evaluation of pilot by surveying non-CRG entities (Jun 2011) - Integration with relevant non-CRG induction/mentoring schemes - Addition of training materials to IMS area of Cochrane Training website |
| Progress since Keystone | - Non-CRG entities advised of pilot in September 2010 - Super User Guide to Archie for non-CRGs released and uploaded to Support section of IMS website - Induction checklists specific to each entity type finalised - Webinars for Fields held in December 2010 (attended by 5 people) - Webinars for Centres and Branches held in January 2011 (15 people) - Webinars for Methods Groups scheduled for beginning of March |
| Progress since Split | - Webinars for Methods Groups held in March 2011 (attended by 7 people) - In total, six webinars were held as part of the pilot, attended by 30 Super Users (10/13 Centres; 7/14 Methods Groups; 5/11 Fields represented) - Two IMS Bulletins for Non-CRG Super Users published and sent to all non-CRG Super Users - Each entity has been assigned an IMS support person to provide individual support as required - Survey conducted in July (responses from 55% of non-CRG entities), finding a generally positive response to the pilot, and identifying that a significant number of entities had not yet accessed training - The scope of future training and support is dependent on decisions about continuation of IMS Support to be discussed in the review of mentoring schemes outlined above; the IMS and non-CRG Execs will participate in the review |

| Title | Editorial Resources Committee |
| --- | --- |
| Description or purpose | Dedicated research assistant support to the Editorial Resources Committee |
| Start–finish date | January 2011 to March 2012 |
| Interim steps | - An agreed prioritisation process to identify future ERC projects - Appointment of part-time research assistant to support ERC document development by coordinating collection of resource material, conducting consultation with all Cochrane entities, and assisting in drafting documents (January 2011) - Agreed ERC work plan for 2011 |
| Progress since Keystone | - The ERC has agreed in principle to ensure that priorities for future ERC projects are in line with Collaboration priorities, and is in close communication with the CEU and MARS to ensure this occurs as the standards are developed - Research Assistant commenced February 2011 and is supporting the committee one day a week, based at the ACC with the ERC Convenor, Miranda Cumpston - A draft workplan will be reviewed at the next meeting of the ERC, which is planned for March 2011 |
| Progress since Split | - A workplan has been finalised and progress against the plan is now regularly monitored at each meeting - Due to her appointment as Training Co-ordinator, Miranda Cumpston will be stepping down as ERC Convenor from the Madrid Colloquium; to be confirmed at that meeting, it is likely that the convenorship will be taken over jointly by Emma Welsh (ME, Airways Group) and Rachel Marshall (or another CEU representative) - As the new co-convenors are both based in the UK, the research assistant has ceased work at the ACC; funding will be reallocated in a manner to be agreed with the new co-convenors (likely to be the CEU); given the short period of time worked, the ACC will not claim against the allocated funding for this project |

| Title | Annual training for methodologists (and those taking responsibility for implementation of methodology) |
| --- | --- |
| Description or purpose | Annual face-to-face training event to be hosted by a Methods Group focusing on generic methodology (Statistical, Bias, Applicability and Recommendations, Information Retrieval) |
| Start–finish date | Ongoing |
| Interim steps | - Methods Board to negotiate order of hosting (by Methods Groups) of the training event and the key topics for the first three years - Processes for prioritising future topics and evaluating training events to be established |
| Progress since Keystone | - 2011 event will be run by Applicability and Recommendations Methods Group (provisionally set for 20-21 June in Berlin) on issues related to Summary of Findings tables - 2012 event will be run by the Bias Methods Group - Presentations (slides and audio) from Statistical Methods Group training course in Cardiff in March 2010 are now available on the SMG website |
| Progress since Split | 2011 event hosted by Applicability and Recommendations Methods Group (30 June to 1 July, Berlin) on GRADE and Summary of Findings Tables (SoF) Network - Purpose was to build an international network of SoF and GRADE experts (MEs, CoEds, methodologists, Centre and Field staff, consumers) who will support authors conducting reviews - 23 participants (10 received stipends, incl. 4 from LMICs) - Spent c.£13K of allocated £20K budget - Positive feedback on the workshop and quality of presenters; there were some requests for extra practical and interactive training involving the software and how to use GRADE before being confident about providing support to authors - Practical lessons learnt will be forwarded to organisers of the 2012 event; these include: >7 weeks’ notification of participation to allow for visas; applications should include a letter of support from an entity; be aware of communication needs of those who speak English as a second language; balance between didactic and interactive learning; make pre-reading available >10 days in advance; need to make very clear purpose to build a network not just for training - Presentations, handouts and online modules will be made available on the Training Website for trainers and users - Follow-up: 2 members have organised GRADE/SoF workshops; 6 members have provided support to authors in co-ordination with ARMG; members have been contacted to be mentored by other ARMG members to provide independent support to authors |

| Title | Biennial training on statistical methods for meta-analysis of Diagnostic Test Accuracy Studies |
| --- | --- |
| Description or purpose | Biennial face-to-face training every two years for Cochrane statisticians and methodologists |
| Start–finish date | July 2011 (then every 2 years) |
| Interim steps | - Revise and update existing DTA workshop materials accordingly - Advertise, run and evaluate workshop |
| Progress since Keystone | - There are no plans for such training in 2011; awaiting confirmation that the two-year cycle (with the information retrieval methods event) will shift a year forward |
| Progress since Split | - Our impression was that there was not an immediate need for this workshop and we decided to shift the two-year cycle a year forward - Before we organise the workshop in 2012, we will first canvass the needs amongst Cochrane statisticians |

| Title | Biennial training in information retrieval methods for reviews of Diagnostic Test Accuracy Studies |
| --- | --- |
| Description or purpose | Biennial face-to-face training every two years for Cochrane TSCs in the various aspects of study identification |
| Start–finish date | July 2012 (then every 2 years) |
| Interim steps | - Revise and update existing DTA workshop materials - Advertise, run and evaluate workshop |
| Progress since Keystone | - Training event not scheduled until 2012 (pending re-scheduling of statistical methods training) |
| Progress since Split | - Pending the re-scheduling of statistical methods training this training event will probably be postponed to 2013 - We will canvass the Information Retrieval Methods Group and the TSC network to identify the needs and may change the 2-year cycle accordingly |

| Title | Cochrane Training Co-ordinator |
| --- | --- |
| Description or purpose | Establish the position of Training Co-ordinator |
| Start–finish date | From January 2011 |
| Interim steps | - Appoint a full-time Training Co-ordinator to implement and coordinate training projects within the Collaboration. This position should be based at a training Cochrane Centre (may be split across two sites if appropriate e.g. to engage specific expertise). |
| Progress since Keystone | - Delay in the appointment process, largely due to workload issues - Main duties of the Training Co-ordinator have been identified; the position description and recruitment process is expected to be agreed by the end of March and the successful candidate in place by June/July 2011 |
| Progress since Split | - Miranda Cumpston (trainer at the Australasian Cochrane Centre) started in the role of Training Co-ordinator in August 2011 - A priority workplan for the remainder of 2011 has been agreed with the TWG co-convenors, and a complete workplan for 2012 will be presented to the TWG meeting at the Madrid Colloquium - Training Co-ordinator has begun discussions with individuals and entities to discuss current projects, future roles and opportunities for collaboration, including Centre trainers, CEU, Handbook Editors, MECIR working group, Methods Co-ordinator, Consumer Co-ordinator, IMS and Web Team; meetings will be held in the UK ahead of the Madrid Colloquium to further these discussions - Training Co-ordinator will present to the MEs and Centre staff (and others to be confirmed) in Madrid, and will be available throughout the Colloquium at the Cochrane Exchange to discuss training needs and projects, and to demonstrate online training resources |

| Title | Cochrane Trainers’ Network |
| --- | --- |
| Description or purpose | Network of people actively involved in developing training materials and/or providing training |
| Start–finish date | September 2010 |
| Interim steps | - Define scope, membership and operation of the Network - Convene meeting at Keystone Colloquium of trainers from all Centres and Branches, plus other entities with a training remit - Set up email list and trainers page on the training website |
| Progress since Keystone | - Inaugural meeting of the Network was held at the Keystone Colloquium and attended by 35 people - Consensus around purpose and scope of the Network (i.e. to strengthen capacity for training across the Collaboration by serving as the principal forum for trainers and those involved in developing training materials) but divergent views on what materials should be made available, to whom they should be made available and with what restrictions - Little has happened since the meeting, pending the appointment of the Training Co-ordinator |
| Progress since Split | - Agreement was reached at the TWG meeting on 18 August 2011 on the procedure for inviting members of the Trainers’ Network, and the conditions under which standard training materials will be shared within this group: - Members will have standing permission to modify materials in accordance with local needs and preferences for the purposes of presenting training on behalf of the Cochrane Collaboration or a specific Cochrane entity, although using unmodified materials is preferred - Approval is not required for every new version, but substantive modifications should be submitted to the Training Co-ordinator for information to identify any possible concerns with altered content, and to collect ideas for improvements to standard materials - Centrally developed materials should always be acknowledged as such - Members may share materials with colleagues for the purpose of presenting training on behalf of the Cochrane Collaboration or a specific Cochrane entity - Permission should be requested from the Training Co-ordinator for any other use of the materials - Preliminary membership of the Network has been established based on the attendees of the meeting in Keystone; the Training Co-ordinator will invite all entities to nominate additional members ahead of the Madrid Colloquium (in stages, beginning with Centre trainers) - The Trainers’ Network email list, Archie folder and password-protected area on the Cochrane Training website have been established, managed by the Training Co-ordinator |