2010 Cochrane Colloquium (Keystone) report

Report prepared by: Robert Dellavalle, Lisa Bero, and Kay Dickersin

for the local organizing committee, 3 March 2009

| Item | Progress |
| --- | --- |
| Date | 18-22nd October 2010. |
| Venue | The University of Colorado has contracted the Keystone Convention Center for October 17-23 2010. Keystone is a principal scientific convention centre in the US that can accommodate the required number of breakout rooms. The conference will be a five-day Monday to Friday meeting based on the program of the Freiburg 2008 Colloquium (with Thursday afternoon free). This conference will be the first Co-Colloquium with The Campbell Collaboration, with Campbell contributing ~20% of the participants. The theme is 'Bringing Evidence-Based Decision-Making to New Heights'. The venue can accommodate from 500 to 1000 participants. The expected registration fee for the initial proposal was $850 US. Rooms will range in price from ~90-150 US. Shuttle transport will likely cost $150 r/t between the airport and Keystone resort. Numerous precautions and warnings regarding altitude sickness will be employed. |
| Hotels | The venue contract guarantees 920 room nights with Keystone resort hotels within walking and/or shuttle distance. (Onetime option to decrease room night commitment by 10% if requested in writing before January 17, 2010) |
| On-site conference manager | An RFA to select a professional conference organiser (PCO) will occur in the Summer of 2009. |
| Local committee | The local organising committee consists of members of the US Cochrane Center and Branches. Organizing conference calls are held and recorded monthly using the Internet tool 'Elluminate'. Several influential Cochrane supporters are being approached to serve in an advisory capacity and to help with awareness raising and potential fund-raising. |
| Insurance | The University of Colorado has signed a Memorandum of Understanding with The Cochrane Collaboration. Cost for cancelling the conference completely ranges from $10,000 US for cancellation before October 17, 2009 to ~$120,000 immediately before the event. Insurance has not been purchased. Quotes for event insurance will be re-examined in October 2009. |
| Promotion and website | A postcard was distributed in Freiburg in 2008. The website will use Regonline.com and potentially any transferable software used in Singapore. |
| Grants and sponsorship | Approximately $50,000 US has been secured in seed money and grants for information technology speakers for the meeting from the University of Colorado. The local organizing committee and the sponsorship committee will likely be merged for this Colloquium. |