Enhancing global participation in The Cochrane Collaboration: Developing the 
Cochrane Academy

Submitted by: 	Jeremy Grimshaw and Peter Tugwell

Date:			31 March 2012

Purpose
This paper updates the CCSG on progress made towards developing the Cochrane Academy to enhance global participation in The Cochrane Collaboration, and requests additional funding to support initial Cochrane Academy sites.

Urgency 
Medium.

Access 
Open Access.

Background
Since its inception, The Collaboration has been committed to engaging individuals around the world in the conduct and use of systematic reviews relevant to their healthcare decision needs. To date, we have made substantial progress with over 28,000 individuals from 109 countries currently involved with the Collaboration. Twenty per cent of the contact authors of Cochrane reviews come from lower- and middle- income countries (LMICs). Many entities (for example, the Infectious Diseases, HIV/AIDS and EPOC review groups) have worked to engage and support individuals in LMICs. We have a number of Centres and Branches in LMICs. Strategic approaches to priority setting have drawn greater attention to the need for reviews relevant to the global burden of disease and stakeholders in LMIC settings. Nevertheless, the Collaboration is aware that it could improve global participation in its activities and the relevance of our reviews for all citizens of the world. The majority of entities and Collaboration leaders are based in developed country settings (especially Australia, Canada and Europe). The 2009 Strategic Review recommended that the Collaboration should ‘Review terms of reference, number and geographic spread of Cochrane entities to ensure efficient alignment with the purposes of the Collaboration’.

To address these issues, the Strategic Session during the mid-year meetings in Split on 30 March 2011 focussed on ‘Ensuring The Cochrane Collaboration enables better global participation’. This session was attended by over 100 individuals from across the Collaboration in person and using web enabled technology. One of the potential strategies identified during this session was the establishment of a formal training and mentoring programme to support first-time authors to complete high quality reviews (a ‘Cochrane Academy’) (see Appendix 1 – relevant section from Report). This received a high level of support from participants in the session and in subsequent discussions. The CCSG agreed in principle to consider a funding proposal to support the initiative.

Since the Split meeting the Co-Chairs and Peter Tugwell have been liaising with various key external stakeholders about how best to achieve the aims of the Cochrane Academy. There was universal support for the proposed Cochrane initiative, with recognition that this was a major initiative for the Collaboration to undertake. There was recognition of the benefits of building capacity in systematic reviews within LMIC settings to enhance use of evidence in healthcare decisions and to strengthen the research infrastructures. All stakeholders, however, strongly recommended that the Cochrane Academy focus upon building relationships and capacity with institutions/groups rather than individuals (mainly due to concerns about the mobility of individuals and potential loss of capacity if individuals leave their original country). In addition, they highlighted the possibilities of leveraging funding from institutions and national and international funders and donors to extend the impact of the proposed Cochrane Collaboration funding and to increase the likelihood of sustainability of funding. We were advised to establish this initiative in one to two sites in the first year and use this as an exemplar in a future meeting with national and international funders (possibly around the second Global Health Systems Research Conference planned for Beijing in November 2012).

The CCSG considered initial funding for the Cochrane Academy at its Madrid meeting in October 2011. Item 16 of the minutes of that meeting notes:

There was broad support for the direction of travel, but there was a general view that the primary purpose of establishing a Cochrane Academy should be developing partnerships and capacity-building rather than funding the preparation of reviews. It was agreed that the involvement of people from low- and middle-income countries in the further development of the proposal would strengthen it. The Steering Group was reminded of its decision in Split to provide an indicative budget of 300K GBP over three years to support all the initiatives discussed, although it was recognized that the Cochrane Academy was likely to require the greatest financial support. There was strong support for approving the proposed budget of 25K GBP per year for three years on two sites, i.e. a total of 150K GBP, with the expectation of additional funds being obtained from partner organisations. It was recognized that there might be additional requirements for relevant entities, and this should be considered. Jeremy was asked to provide a detailed implementation plan, incorporating Steering Group members’ feedback, for discussion at the next face-to-face meeting.

Action: Jeremy to provide a detailed implementation plan for discussion at the next face-to-face meeting in Paris in April 2012. Nick to add 50K GBP per annum for three years to the cash flow forecast.

Progress since Madrid
Since then Peter Tugwell has established an advisory group for this initiative including key internal and external stakeholders, and has consulted widely. The members of the Cochrane Academy Advisory Group are:

- Peter Tugwell (Chair)

- Jeremy Grimshaw (Co-Chair, CCSG)

- Andy Haines (London School of Tropical Health and Hygiene and former Chair of the WHO Advisory Committee on Health Research)

- Steve McDonald (Centre representative, CCSG)

- Zulma Ortiz (Chief of Epidemiologic Research and Training Department, Epidemiologic Research Institute, National Academy of Medicine, Buenos Aires)

- John-Arne Røttingen (Chair of the Board of the WHO Alliance for Health Policy and Systems Research)

- Tessa Tan Torres (Economic Evaluation of Health Systems, World Health Organization, Geneva, and Professor of Medicine, University of Philippines, Manila, Philippines)

- David Tovey (Editor in Chief, The Cochrane Library)

- Jimmy Volmink (Director, South African Cochrane Centre)

- Howard White (Executive Director of International Initiative for Impact Evaluation (3ie) and Co-Chair of Campbell Collaboration International Development Review Group)

The Advisory Group met by teleconference in February 2012. They expressed support for the initiative and raised a number of key issues including:

- The importance of not raising undue expectations initially;

- The importance of having a streamlined application process (rather than an open call which would likely incur significant burden on the global research community);

- Initially building on existing platforms with a critical mass of systematic review experience such as those supported by the Alliance of Health Systems Policy and Research

- The importance of establishing 3-4 centres to demonstrate the commitment of The Cochrane Collaboration to this area.

Following the Advisory Group meeting, Peter Tugwell proposed the following timescale:

February 2012		Formation of Steering Group and Teleconference to agree on TOR

April 2012		Call for expression of interest

May 2012		Deadline for expressions of interest

June 2012		Full applications received and peer review

July 2012		Pilot the Cochrane Academy sites established

September 2012	Report to Cochrane Collaboration Steering Group in Auckland

November 2012 	Meeting of funders and donors in Beijing

We are currently in the process of identifying potential sites (based on internal and external stakeholder consultation (e.g. with the Alliance of Health Systems and Policy Research) who will be invited to submit an expression of interest. We envision approaching no more than 8-10 groups, shortlisting 4-6, and funding 4 sites.

In addition, George Mason University (GMU) (the site of one of the US Cochrane Colleges) has expressed a willingness to provide partner funding and a meeting with senior representatives of GMU is planned alongside the Paris mid-year meetings. We have also had positive initial discussions about potential co-funding arrangements with the Alliance of Health Systems and Policy Research and 3ie. Further, Tim Evans (Dean of the James P Grant School of Public Health, BRAC University, Bangladesh, and former Assistant Director General with responsibility for Evidence, Information, Research and Policy at WHO) who is helping organize the 2nd Global Health Systems Research Conference has offered to convene a meeting of potential funding partners alongside this conference (assuming that The Cochrane Collaboration makes significant progress over the next six months).

Summary
Since Madrid, we have established a Cochrane Academy Advisory Group that supports the proposed initiative but strongly recommends increasing the initial investment to 100k GBP per annum for three years (to demonstrate our commitment to this initiative) and an invited, not open, commissioning process in the first instance. We have identified a potential funding partner and have commitment to convene a funding partner meeting alongside the 2nd Global Health Systems Research Conference in Beijing. The long-term vision would significantly lever the initial investment by The Cochrane Collaboration through partnership with other funders to enhance the total amount of funding and number of Cochrane Academy sites.

Budget justification
The CCSG provisionally agreed in Split to provide GBP 100,000 per year for three years to enable better global participation in The Cochrane Collaboration. In Madrid the CCSG agreed a request for 50,000 GBP for three years to support the establishment of the Cochrane Academy. This paper requests a further 50,000 GBP per year for three years for the Cochrane Academy to support an additional two sites, thus demonstrating our commitment to potential funding partners.

Recommendations

1.	That the CCSG approves the proposed plans to establish the Cochrane Academy and to seek additional funding partners.

2.	That the CCSG approves an additional 50K GBP per year for three years to support the establishment of pilot sites.

Appendix 1 - Report from the Strategic Session in Split

| Cochrane Academy A formal training and mentoring programme to support first time authors (‘fellows’) to complete high quality reviews |  |
| --- | --- |
| Key Components | - Leadership of academy - Selection of faculty and mentors - Selection of authors and review topics - Methods, mode & place of training |
| Critical Success Factors | - Good communication between Academy, Centres and CRGs - Ensuring faculty and mentors have appropriate training, methodology and content expertise - Ensuring appropriate selection of fellows and review topics including equity in terms of gender, geography, age, profession - Definitions and expectations - Funding - Development of Academy program - Training materials - Academic credibility and credits - Assessment of fellows needs for support and matching of fellows with faculty/mentors |
| Resource Implications | - High resource requirements - Fellowship support (potentially including, travel, accommodation, living expenses, etc for fellows) - Support for entities/individuals providing expertise - Training materials (some exist but additional development may be needed) |
| Measures of Success | - Process - Numbers of high quality applications received - Number of faculty members/mentors recruited - Outcome - Numbers of reviews/updates produced by fellows during Academy program - Impact - Numbers of reviews/updates produced by Academy graduates - Numbers of new authors mentored by Academy graduates - Levels of participation in Cochrane by Academy graduates |
| Required Actions | - Ascertain sources and level of funding available - Appoint Academy leaders - Develop objectives for the Academy - Define - what support/programs will be delivered by the Academy - expectations of faculty/mentors and fellows - Develop processes for - application for admission, including eligibility criteria - selection of fellows and review topics - identifying, selecting, managing faculty/mentors - assessing fellows’ needs for support - matching fellows with faculty/mentors - coordinating fellowship program - evaluating progress of fellows - determining effectiveness of Academy - Work with Training Working Group to identify what training materials are available - Identify mentoring experience within the Collaboration and determine what does and doesn’t work |
| Issues to be considered | - Coordination across sites - Sustainability - Develop programme to support local trainers - Identify regional organisations/infrastructure - Ask Cochranites in low participation areas to identify potential candidates - Support structures and distance/remote participation - Mentor selection to address - Personal support and/commitment - Willingness - Time - Expertise - Collaboration networks - Definition - Knowledge of the Cochrane Collaboration process - Clarity/breadth of definition - Mix of models - Concrete/negotiated |