Co-ordinating Editors’ Executive report/work plan for 2011-2012

| Task | Member of exec who is co-ordinating task | Timelines |
| --- | --- | --- |
| PERFORMANCE INDICATORS |  |  |
| Analyse job description survey of CoEds | SH and exec | Done. |
| Develop key performance indicators for CoEds | CEU and exec | Discussed in Split |
| Work with MEs and TSCs to develop key performance indicators for CRGs | CEU and exec | Discussed in Split |
| Comment on key performance indicators for the CEU | All exec | Discussed in Split |
| Integrate key performance indicators into MaRC processes | CEU and exec | Madrid and ongoing, with work led by CEU |
| TRAINING |  |  |
| CoEd member of Training Working Group; contribute to the Cochrane Training Proposal for CCSG | RC and exec | ‘Cochrane Training’ proposal approved by CCSG and Training Oversight Committee (name TBC) established; projects underway and work continuing |
| CoEd member of MECIR Coordinating team; contribute to development of training and roll-out of MECIR standards | RC | Ongoing. |
| METHODOLOGICAL STANDARDS |  |  |
| Co-convene MARS | RC | MECIR initiative: conduct standards developed and agreed. Reporting standards for consultation Jan-Feb 2012. New Coeds added to MARS. |
| MECIR Coordinating team | RC | Response to feedback on reporting standards. Amendment of reporting standards. Next draft for completion May/June 2012. |
| Co-convene MECIR groups developing standards | All | 2011 |
| Development of reporting standards for plain language summaries | RC | Initial standards from PLEACS work combined with MECIR reporting standards. To be included in next draft for completion May/June 2012. |
| Discuss/approve standards | All | Staged, ie Split and Madrid. Board to discuss implementation issues and initial reporting standards in Paris, April, 2012. |
| Integrate standards into KPI processes | All | Ongoing. |
| THE COCHRANE LIBRARY |  |  |
| Work with David Tovey and the CEU on key initiatives as required, eg audit of abstracts, strategic session for Paris. | All | Continuing. |