Fields’ Executive report to the Steering Group

1. PRELIMINARY INFORMATION

- Entity Executive:  Fields’ Executive

- Meeting: Colloquium meeting, Auckland, September 2012

- Report period: April-September 2012

- Members of the Executive for this period:

  - Denise Thomson (Chair and CCSG representative), Child Health Field

  - Catherine Gallagher, Justice Health Field

  - Kathy Mahan, Neurological Field

  - Alan Pearson, Nursing Care Field

  - Susan Wieland (Monitoring and Registration Committee representative), Complementary Medicine Field

- Report prepared by: Denise Thomson

- Access: Open

- Purpose of report:

- Scheduled update

- Low urgency

2. WORKPLAN UPDATE

i) For this reporting period:

| Objective/planned activity | Planned and/or achieved output | Timeline and comments | Allocated budget |
| --- | --- | --- | --- |
| Meetings |  |  |  |
| Fields Executive meeting at the Paris mid-year meeting | Planning and goal-setting for the upcoming year | 16-17 April 2012 |  |
| Regular teleconferences | Ongoing communication and planning | Ongoing | None |
| Training and mentoring procedures for Field entity staff |  |  |  |
| Training and mentoring for the Prehospital and Emergency Care Field | Full-day meeting in Paris, 13 April 2012, with Patricia Jabre, Field Director, Philippe Ravaud, Director of the French Cochrane Centre, and several other staff, advisory board members and a funder. | 13 April 2012 |  |
| Mentoring to the Developing Countries Field | Ongoing communication and support. | Ongoing | None |
| Cochrane Collaboration projects |  |  |  |
| Participation in the planning for the 2013 celebrations of the 20th anniversary of the Cochrane Collaboration. | Field perspective represented in planning; news about, Ongoing and plans for, the celebration are disseminated to Fields’ stakeholder groups. | Ongoing | None |
| Participation in the working group developing a policy on access to trial data | Field perspective represented in developing the Collaboration’s policy in this important area | Ongoing | None |

ii) Full breakdown of expenditure:

| Activity | Amount allocated |
| --- | --- |
| Attendance at the Paris meetings | 6,077.48 GBP |

iii) Meetings, teleconferences and other communication:

Face to face meetings – 16 and 17 April, Paris

Teleconferences – 8 August

iv) Descriptive summary:

What were the priorities for your executive and respective constituency during this reporting period? What were your main activities? What were your challenges and achievements? Are there any important updates that the Steering Group should be aware of?

At the Paris meeting, the Fields Executive set the priority for the upcoming year to be supporting and mentoring potential or existing Fields.  This was done as follows:

- We have heard from a group proposing to establish a Nanotechnology Field and have set a meeting in Auckland to discuss this further.

- We held an all-day meeting on 13 April with Dr. Patricia Jabre, Director of the new Prehospital and Emergency Care Field, Dr. Philippe Ravaud, Director of the French Cochrane Centre, and several other people connected with the Field.  This was a very productive and useful meeting – feedback we received after the event was that those in attendance were newly aware of the complexity of carrying out a Field’s mandate and felt better prepared for taking on this work.  This meeting allowed us to pilot-test training and mentoring materials we had developed.

- We have been working with Dr. Mario Tristan of the Developing Countries Field.  In particular, our MaRC representative, Susan Wieland has maintained close contact with Dr. Tristan since then to assist with reporting to the MaRC on the current status and activities of this Field.

- We have developed plans to conduct in-person training and mentoring sessions with the Primary Health Care Field, Health Care of Older Persons Field and the Justice Health Field in October 2012, March 2013 and May 2013, respectively.

3. OBJECTIVE PLANNING

i) For the next reporting period and beyond:

| Objective/activity | Planned output | Timeline and comments |
| --- | --- | --- |
| Training and mentoring procedures for Field entity staff |  |  |
| Continued work on training and mentoring materials for Fields staff. | Mentoring program in place; training materials finalised. | We have developed materials and have plans in place for support and mentoring for proposed, new and existing Fields. |
| Meetings |  |  |
| Fields meeting and Fields Executive meetings, Auckland Colloquium | Ongoing planning and communication. | October 2012 |
| To hold frequent teleconferences to carry out the work of the Executive. | Ongoing planning and communication. | Ongoing |
| Fields Executive meeting, April 2013 | Ongoing planning and communication. | April 2013 |
| Cochrane Collaboration projects |  |  |
| To participate in the planning for the 2013 celebrations of the 20th anniversary of the Cochrane Collaboration. | Field perspective represented in planning; news about, and plans for, the celebration are disseminated to Fields’ stakeholder groups. | Ongoing |
| Developing communication and collaboration between Fields, and between Fields and Executive |  |  |
| Developing a webspace for Cochrane Fields | Fields website. | December 2012 |

4. FUNDING AND/OR POLICY DECISION REQUESTS

Are members of your entities submitting any proposals to the Steering Group for decision at its next meeting? If so, how do these fit with the wider goals of your entities?

None of which we are aware.

5. ANNEXES TO THIS REPORT

None.