Editor in Chief’s report and work plan

Contents

Purpose	2

Urgency	2

Access	2

Background	2

Progress against objectives	3

Objectives	4

Additional activities	6

Publications	7

Proposals and discussion – work plan	7

1. Improving the quality of our output	7

2. Downstream product development	8

3. Collaboration development	8

4. Projects in development	9

Summary of recommendations	9

Resource implications	9

Impact statement	9

Decision required	10

Appendices: Projects list January 2010	11

Appendix 1. Improving the quality of our output	11

1.1. In progress	11

1.2. In development	22

Appendix 2. Downstream product development	24

2.1. In progress	24

2.2. In development / under consideration	27

Appendix 3. Projects: Collaboration development	28

3.1. In progress	28

# Purpose

This paper aims to provide an evaluation of progress made to date against the objectives set for the Cochrane Editorial Unit (CEU) and also a work plan for the time period up until the end of the 2010–2011 financial year.

# Urgency

High.

# Access

This is an open access paper.

# Background

The Strategic Review of The Cochrane Collaboration, and also the Melbourne Cochrane Library Summit, identified important and urgent priorities for the development of The Cochrane Library. In addition, in my first year as Editor in Chief, the point was repeatedly made that members of the Collaboration at all levels, and across entities, felt that the need for change was great. Concerns about review quality within the Collaboration were also a key driver in the desire to appoint an Editor in Chief. Since review quality is seen externally as a core Cochrane advantage, addressing this issue alongside improving the presentation of content within The Cochrane Library has been the highest priority.

At the 17th Cochrane Colloquium, held in Singapore in October 2009, my report identified a number of key objectives for the next 12 months. These are as follows:

- Completion of the evaluation of the self-audit. Agree learning and action points and develop action plan to follow through on agreed changes in process across the Cochrane Review Groups (CRGs).

- Work with the Monitoring and Registration Group to reduce duplication of effort and ensure that monitoring and oversight of Cochrane Review Groups are co-ordinated and appropriate.

- If go-ahead given by the Cochrane Collaboration Steering Group (CCSG), create Cochrane Response service, and complete first five projects, including timely delivery of current commissions. Initiate evaluation.

- Submit proposal to the UK National Institute for Health Research (NIHR) for funding for initiatives related to increased engagement of users and innovation: overviews and/or updating and/or different types of review.

- Complete prototype and pilot stage for “Cochrane PICO” if go-ahead given by the CCSG.

- Roll out phase one enhancements to web presentation, including increasing frequency of publication, improved browse function, changes to navigation, appearance, and utility, at both the website level and article level (for Cochrane Reviews).

- Work with the Publishing Policy Group on proposals for changes to the continuity and cross-linking of publication records.

- Initiate activities aimed at developing core standards for reviews published in the Cochrane Database of Systematic Reviews (CDSR).

- Develop and commence programme aimed at improving updating performance of the CDSR.

- Develop and commence programme aimed at improving feedback performance of the CDSR.

As the next few sections demonstrate, we have made considerable progress against these objectives even at this early stage. This has been achieved only by enormous and unsustainable effort on behalf of the CEU team, working long days and also weekends. The CCSG should also bear in mind the range of tasks outside these objectives that have been delivered. These include:

- Co-ordination of the Evidence Aid content for cochrane.org;

- Work in support of the Consumer Strategic Session at the mid-year meeting;

- Responding to queries from within the Collaboration and from stakeholders;

- Assessing each published issue for potential reviews suitable for press release;

- Organizing and co-ordinating Cochrane meetings; and

- Setting up and staffing the CEU office from scratch.

# Progress against objectives

In this section, I describe the CEU’s performance against the objectives agreed at the 2009 Singapore Colloquium. Table 1 gives an overview of the CEU objectives, the status of progress, and how each objective relates to the Strategic Review recommendations. This is followed by details of the progress made for each objective as well as a list of publications from the CEU.

This is followed by the CEU work plan, which the CEU developed after the Singapore Colloquium, and is intended to describe the CEU’s objectives up to end of the financial year 2010–2011. The work is divided into projects to provide measurable and defined outcomes.

Table 1. Overview of CEU objectives, status, and relation to Strategic Review

| Objective (in brief) | Status | Relation to Strategic Review recommendation |
| --- | --- | --- |
| 1. Self-audit and follow-up action plans | In progress | 1. Performance on quality development in relation to Cochrane Reviews |
| 2. Reduce duplication and improve process of monitoring of Cochrane Review Groups | No progress | — |
| 3. Set up and initiate Cochrane Response | Achieved | 1. Performance on quality development in relation to Cochrane Reviews |
| 4. Funding proposals to the UK NIHR for initiatives related to increased engagement of users and innovation | Achieved | — |
| 5. “Cochrane PICO” prototype and pilot | Achieved | 5. Principles for new products |
| 6. The Cochrane Library publication frequency and online developments | Achieved/in progress | 2. Improving the usability of The Cochrane Library |
| 7. Continuity and cross-linking of publication records | In progress | — |
| 8. Develop core standards for Cochrane Reviews | In progress | 1. Performance on quality development in relation to Cochrane Reviews |
| 9. Improve updating performance in the CDSR | No progress | — |
| 10. Improve feedback performance of the CDSR | No progress | — |
| Additional activity: Cochrane Journal Club [no objective set in Singapore] | In progress | 3. Cochrane Education |
| Additional activity: Dr Cochrane [no objective set in Singapore] | Limited progress | 3. Cochrane Education |

## Objectives

### Objective 1: Completion of the evaluation of the self-audit. Agree learning and action points and develop action plan to follow through on agreed changes in process across the Cochrane Review Groups.

The self-audit of CRG processes was presented to the Singapore Colloquium and has been effective in enabling CRGs to build self-awareness, and importantly to compare themselves with others. Since Singapore, the CEU has organized meetings with CRGs to help them to reflect on their processes and use the experience to create an action plan. Each meeting lasts about two hours and involves preparation by the CRG and the CEU to ensure that it is an effective meeting. To date (February 2010), we have met with the following CRGs, either in person or with a teleconference: Acute Respiratory Infections; Airways; Depression, Anxiety and Neurosis; Effective Practice and Organisation of Care; Gynaecological Cancer; Multiple Sclerosis; Upper Gastrointestinal and Pancreatic Disorders; and Wounds.

### Objective 2: Work with the Monitoring and Registration Group to reduce duplication of effort and ensure that monitoring and oversight of Cochrane Review Groups are co-ordinated and appropriate.

No progress made to date.

### Objective 3: If go-ahead given by the CCSG, create Cochrane Response service, and complete first five projects, including timely delivery of current commissions. Initiate evaluation.

The CEU was delegated the task of introducing a Cochrane Response service. This has already resulted in commissions of multiple update projects from the UK NIHR and the World Health Organization. The CEU has supported and brokered these, and they have resulted in the successful completion of one project (influenza review updates), and have brought income, or the promise of income, to a number of CRGs (about £50,000 in total to date).

### Objective 4: Submit proposal to the UK National Institute for Health Research (NIHR) for funding for initiatives related to increased engagement of users and innovation: overviews and/or updating and/or different types of review.

We submitted three separate collaborative bids (as follows) to the NIHR Cochrane-NHS Engagement Awards totalling over £300,000 and were named co-applicants on two other proposals.

- “Updating: prioritization based on stakeholder needs and centralised updating support for high-priority Cochrane Reviews”: This is a project that incorporates engagement with NHS stakeholders, development of the updating tool, and customised support to self-selected Cochrane Review Groups.

- “Summary of findings tables in Cochrane Reviews: uptake, development and dissemination”: This is a project aimed at training end users and authors of Cochrane Reviews.

- “Cochrane PICOs: Innovative and interactive summaries of Cochrane Reviews”: This is a project aimed at further developing the Cochrane PICO template based on the results of user testing and also supporting the creation of a minimum of 50 new Cochrane PICOs.

### Objective 5: Complete prototype and pilot stage for “Cochrane PICO” if go-ahead given by the CCSG.

The major work in this category has revolved around the successful completion of the first phase of the Cochrane PICO pilot. This project was also conducted within challenging timeframes to ensure that user testing could be completed by the time of the mid-year meeting. This activity included designing and consulting on suitable templates for Cochrane PICO, communicating with volunteers who had offered to prepare example Cochrane PICOs, and editing these for style and content.

We will present the current state of play jointly with our colleagues from Wiley-Blackwell to the mid-year meeting in Auckland. This will include preliminary results of user testing.

We have now received example Cochrane PICOs from the following review groups: Cochrane Airways Group; Cochrane Infectious Diseases Group; Cochrane Renal Group; Cochrane Neonatal Group; Cochrane Musculoskeletal Group; South Asian Cochrane Centre; and the Cochrane Iberoamerican Centre.

Also, the Child Health Field and Dutch Cochrane Centre have expressed interest in this project, as have other CRGs.

The testing to date has raised a number of issues relating to the most appropriate format, readability of abstracts in general, and this has led to a re-evaluation of the project. We intend to come to Auckland with costed and scoped proposals for the CCSG to consider. One important issue is that of ownership. The current pilot was partly supported by Wiley-Blackwell, although it has relied on the goodwill of numerous authors also. The CCSG will need to decide whether and to what extent it is prepared this project in the light of user testing.

### Objective 6: Roll out phase one enhancements to web presentation, including increasing frequency of publication, improved browse function, changes to navigation, appearance, and utility, at both the website level and article level (for Cochrane Reviews)

The web programme, co-ordinated with our publishers, Wiley-Blackwell, the Freiburg web team and the IMS team in Copenhagen, has begun the process, identified as a priority recommendation in the Strategic Review, of improving the presentation of Cochrane Reviews to our audience.

From January 2010, the CDSR, and the ‘About The Cochrane Collaboration’ database, have been published monthly. This also coincided with improvements in the header information for reviews and protocols, and much-needed improvements to the presentation of search findings.

In March 2010, we will see the introduction of phase two of the web programme, with a new homepage for The Cochrane Library. The homepage will have a modern “look and feel” and will be easier for end users to navigate. It includes a new “browse by clinical specialty” function for Cochrane Reviews, an Editorial (for each new issue), Special Collections (to highlight groups of reviews, such as in response to topical issues), and “push” functions such as an RSS feed and email alerts. The various web pages with supporting information, such as “About The Cochrane Library” have also been redrafted with improved linkage to Cochrane.org.

Developing the browse function and other features has been a considerable undertaking. This included the task of creating a user-intuitive structure, and matching reviews to this. The work was initially scoped as taking nine months, but we needed to accelerate the preparation to meet the deadlines for the technical development in order to be ready for the March launch. This proved a considerable task, and we would acknowledge that despite successfully completing it in time, there were ramifications for other competing projects which were delayed.

The CEU team and colleagues at Wiley-Blackwell also identified the importance of maintaining good communications with other stakeholders within the Collaboration, and as the relatively painless introduction of monthly issues has demonstrated, this effort was undeniably a good investment of time.

### Objective 7: Work with the Publishing Policy Group on proposals for changes to the continuity and cross-linking of publication records.

We have submitted a paper on this subject, following feedback, to the Editorial Management Advisory Group (EMAG) and RevMan Advisory Group (RAG) meetings held in London in February. The next stage is to implement the changes in collaboration with the publishers and the IMS team, with further consultation from stakeholder groups. We anticipate the roll-out of changes to have started by the Keystone Colloquium.

### Objective 8: Initiate activities aimed at developing core standards for reviews published in the CDSR.

To be discussed at the April 2010 joint meeting of the Co-ordinating Editors and the Methods Application and Review Standards (MARS) Group. A small group of volunteer Co-ordinating Editors will work on this beforehand.

### Objective 9: Develop and commence programme aimed at improving updating performance of the CDSR.

No progress made to date, although the CEU has been researching options and discussing these with specialists (including information specialists), and planning ahead for taking this forward.

### Objective 10: Develop and commence programme aimed at improving feedback performance of the CDSR.

No progress made to date, although I have been in discussions with the retiring Feedback Management Advisory Group convenor.

## Additional activities

### Cochrane Journal Club

Although I did not set a specific objective for this, this is an ongoing achievement for the CEU.

During the Singapore Colloquium we were able to announce the launch the Cochrane Journal Club. This has been a successful project and, as of end February 2010, four issues of the Cochrane Journal Club have been published covering the following topics:

- Reducing uncertainties about the effects of chemoradiotherapy for cervical cancer: individual patient meta-analysis (Clinical and methodological versions)

- Minimally invasive synthetic suburethral sling operations for stress incontinence in women (Clinical)

- Surgical excision margins for primary cutaneous melanoma (Clinical)

- Biologics for rheumatoid arthritis: an overview of Cochrane Reviews (Clinical and methodological versions)

- Interventions for preventing falls in older people in nursing care facilities and hospitals (Clinical)

Since its launch (7 October 2009) there have been 9,140 visitors to the site, viewing a total of 16,129 pages. The visitors come from 128 different countries/territories, with the following in the top 10 (most visits first): UK; US; Canada; Spain; Australia; India; Italy; Germany; China; and Taiwan.

There have been 786 sign-ups to the Cochrane Journal Club email alert, making it one of the most successful sign-up campaigns at Wiley–Blackwell.

The Cochrane Journal Clubs are now largely self-supporting thanks to the energy and commitment of Professor Mike Clarke from the UK Cochrane Centre and Bryony Urquhart from Wiley-Blackwell, working with the review authors.

### Dr Cochrane

The CEU did not include this as a specific objective, but, if resources allow, we will also make further enquiries into piloting Dr Cochrane as an educational tool alongside the CDSR in the next 12 months. However, it is not currently within our work plan.

## Publications

The CEU has contributed to the publications shown in Table 2.

Table 2. CEU publications

| Publication | Author | Publication status |
| --- | --- | --- |
| - Commentary for the Journal of Clinical Epidemiology on the Methods Articles relating to Comparative Effectiveness Reviews | Tovey D | In print |
| - Editorial for the European Urology Today newsletter | Lasserson T, Tovey D | In print |
| - Letter: The Background Review for the USPSTF Recommendation on Screening for Breast Cancer. Annals of Internal Medicine | Dickersin K, Tovey D, Wilcken N, Ghersi D | Published 15 February 2010, www.annals.org/cgi/content/full/0003-4819-152-8-201004200-00196v1 |

# Proposals and discussion – work plan

We have developed the following work plan building on our objectives and achievements to date. We have divided the plan into discrete projects, each of which is aligned to a strategic objective:

## 1. Improving the quality of our output

| Project | Deliverables |
| --- | --- |
| Cochrane Review Group (CRG) self-audit and editorial standards | All CRGs to have been offered consultation to discuss results of the self-audit; and revised editorial standards document [15 months] |
| Web programme | Improved search function [12 months] Deliver changes to “clarification of content” project: new home pages, and more intuitive navigation for The Cochrane Library and cochrane.org [11–12 months] Commissioning, editing and publication of regular editorials (at least monthly) (ongoing) Updating the browse list with each new Issue of CDSR (ongoing) Building new Special Collections for each new Issue of CDSR (ongoing) |
| Updating programme | 3 discrete projects over 12 months 1. Diagnostic and exploratory project: Identify barriers and facilitators to delivering updated reviews 2. Consultancy project: Support 6 to 8 CRGs in addressing backlog of reviews needing updating. Complete pilot project for self-selected CRGs [12 months] 3. Development plan Develop proposal for further work including outcomes and resources and present to CCSG – 12 months towards objectives stated above – all reviews fit for purpose by end 2012 |
| Continuous publication record | Publication process modified to permit the option for a new protocol as part of an update [12 months] Improved cross-linking between related reviews (i.e. where a review has been split, lumped, or superseded) within Archie, CDSR and PubMed [12 months] Withdrawn category replaced with defined actions for each of the reasons for withdrawal [12 months] |
| Publication ethics | Papers delivered to mid-year meeting of Co-ordinating Editors’ Executive and the Co-ordinating Editors’ Board meeting in April relating to declarations of interest and plagiarism, and successful implementation of recommendations [9 months] |
| Copy-editing: Cochrane Style Guide and Copy Edit Support | All new Cochrane Protocols and Reviews copy-edited by (1) Copy Edit Support or (2) ‘approved’ in-house Cochrane Review Group copy editor [12 months] Copy Edit Support: - Criteria developed and implemented for when a Cochrane Review is ready for copy-editing by Copy Edit Support [6 months] - Process agreed by Co-ordinating Editors for Copy Edit Support to return Cochrane Reviews to editorial teams when problems in review methodology or content identified [6 months] |
| Cochrane Register of Studies | Working closely with the preferred provider (Metaxis) to ensure successful implementation of the proposed solution [1 to 2 years] |
| Implementing PRISMA | The term “systematic review” is included in the Cochrane Review title, preferably outside of CDSR but in the recommended CDSR citation [12 months] A study flowchart included in each new and updated Cochrane Review [12 months] |

## 2. Downstream product development

| Project | Deliverables |
| --- | --- |
| Cochrane Response | Collaboration-wide tender monitoring and alert system set-up [4 months] Complete > 4 commissions of new or updated reviews [12 months] Evaluate initial 12 months, and formulate proposals for service beyond this [15 months] |
| Cochrane PICO | Assist evaluation of pilot and contribute to plans for onwards development for CCSG/Wiley approval [9 months] |
| Cochrane Education | Cochrane Journal Club delivery every 6 weeks [March 2011 ongoing] At least one pilot of the Dr Cochrane educational resource for end users of The Cochrane Library [12 months] |

## 3. Collaboration development

| Project | Deliverables |
| --- | --- |
| Consumer programme/mid-year meeting preparation | Contribution to planning of mid-year meeting [4 months] Development of action plan for after the mid-year meeting [6 months] |
| Editorial management of orphan Cochrane Sexually Transmitted Diseases Reviews | Support authors of existing titles and protocols and arrange editorial review for submitted work [11 months] |

## 4. Projects in development

The following projects are not included within the current proposals, but may impact on future developments.

| Improving management of feedback | Implement changes to ensure that feedback, appropriately edited or reviewed is presented rapidly (within 1 month) in the relevant Cochrane Review. We will also aim to develop proposals that will result in CRGs accepting and implements challenging standards for publishing author responses. |
| --- | --- |
| Cochrane Decision Support | Develop partnership with InferMed, Duodecim, Wiley-Blackwell to develop decision support applications |
| Impact factor project | Implementation of agreed proposals to bolster/improve impact factor [9 months] Rise in impact factor by 2012 |
| Overviews of reviews | Project aimed at boosting the number of overviews included in the CDSR [2 years] |
| Dr Cochrane | Education tool developed in Italy aimed at users of The Cochrane Library |

# Summary of recommendations

We recommend that the CCSG agrees that the projects and timelines included in the paper are satisfactory.

# Resource implications

The Cochrane Editorial Unit budget is discussed in a separate paper.

# Impact statement

Adopting these recommendations will address the key challenges faced by The Cochrane Collaboration that relate to the CDSR over the next 12 to 15 months. They represent a realistic and achievable direction of travel with deliverables that will enhance the offering to end users. The most important elements of these proposals are as follows:

- Impact on updating: Presently there are over 2000 “outdated” reviews within the CDSR. The Updating Working Group recommendation was that the Editor in Chief would assume overall responsibility for improving performance in relation to updating. Currently we do not have resources to work on this.

- Development of Cochrane PICO: This represents a major step towards creating concise, question-driven summaries of reviews for use in underpinning e-textbooks, as a standalone offering, and within decision-support applications.

- Web programme: Improving the usability of The Cochrane Library was a key recommendation of the Collaboration’s Strategic Review.

- Cochrane Response: Also a key recommendation of the Collaboration’s Strategic Review aimed at improving the perceived responsiveness of The Cochrane Collaboration to the needs of users and customers.

- Quality of Cochrane Reviews: We recognise that this is a key concern, and regarded as a unique selling point for the Collaboration. The projects described aim to maintain, harmonise and further develop review quality. We intend to build on work to date, which has concentrated on editorial process, to cover review quality, working with the MARS Group, Co-ordinating Editors and others.

# Decision required

The Steering Group is asked to approve the recommendations of this paper.

# Appendices: Projects list January 2010

# Appendix 1. Improving the quality of our output

For each of these we present a table that includes a summary of the project, responsibilities, outcomes, resource utilization.

## 1.1. In progress

### Project name: Cochrane Review Group self-audit and editorial process/standards document

| Description | To complete the self-audit cycle by meeting with individual CRGs to discuss their responses and follow-up action plans; and to revise the editorial process/standards document in light of the self-audit and feedback from the Singapore Cochrane Colloquium |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | Harriet MacLehose and Toby Lasserson |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - All CRG self-audit meetings completed and each CRG to have action plan - Three CRGs report back on self-audit meeting and present action plan at the Co-ordinating Editors’ Board meeting in April 2010 - Editorial process/standards document revised and agreed by the three Executives (Co-ordinating Editors, Managing Editors, and Trials Search Co-ordinators) - To plan the next self-audit cycle in collaboration with the Monitoring and Registration Group |  |
| Interim steps | - Self-audit: Initial contact letter to all CRGs before end 2009; and visits scheduled at about 1/week with planning time - Editorial process/standards document: Feedback collected and strategy for revision and approval agreed - Liaise with MRG about future audits |  |
| Stakeholders | - Executives (Co-ordinating Editors, Managing Editors, and Trials Search Co-ordinators) - Cochrane Review Groups | - CRG Procedures Collection Working Group - Monitoring and Registration Group |
| Total no. of months | 17 months |  |
| Start–finish date | November 2009 – March 2011 |  |
| Potential for follow-up | Self-audit process will continue in collaboration with the Monitoring and Registration Group |  |
| Resources | Executive lead (Editor): 4 days/month Project management: 2 days/month for first 5 months, reducing to 1 day per month for further 6 months |  |

### Project name: Web programme (1/3) – Move to monthly publication

| Description | Support web programme and ensure successful move to monthly publication for the Cochrane Database of Systematic Reviews |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | Harriet MacLehose and Toby Lasserson |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | Move to monthly publication for the CDSR |  |
| Interim steps | - Wiley and IMS teams: Move to collection and publication of ‘changed data’ only - Review headers and icons: Work with Wiley to agree and introduce relevant changes in the CDSR and, where necessary, Cochrane Policy Manual and Cochrane Handbook - CRGs: Develop roll-out and support strategy to ensure smooth transition to increased publication - Awareness raising: Support Cochrane.org and Wiley teams to promote monthly publication to end users |  |
| Stakeholders | - Wiley-Blackwell - Information Management System team - 3 Executives | - Cochrane Review Groups - Freiburg Cochrane.org web team - Copy Edit Support |
| Total no. of months | 3 months |  |
| Start–finish date | November 2009 – February 2010 |  |
| Potential for follow-up | Possible that follow-up will continue |  |
| Resources | Executive lead (Editor): 3 days/month Project management: 2 days/month |  |

### Project name: Web programme (2/3) – Search and browse in The Cochrane Library

| Description | Support web programme to develop and implement a new search and browse feature in The Cochrane Library |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | Harriet MacLehose and Toby Lasserson |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - New browse structure developed and implemented in The Cochrane Library - New search feature developed and implemented in The Cochrane Library |  |
| Interim steps | - Browse structure: Develop new browse structure and explore with CRGs how this impacts on “topic lists”. - Browse – pre-publication: Liaise with IMS team to explore options for expanding current topics lists to see the browse structure can be implemented in Archie - Browse - publication: Liaise with Wiley to ensure implementation of browse structure in The Cochrane Library - Search: Liaise with Wiley and IMS teams to explore improved tagging (including MeSH) of reviews to improve search function - Search: Liaise with Wiley to ensure a more user-friendly search included in The Cochrane Library |  |
| Stakeholders | - Wiley-Blackwell - Information Management System team | - Freiburg Cochrane.org web team - Cochrane Review Groups |
| Total no. of months | 12 months |  |
| Start-finish date | November 2009 – October 2010 |  |
| Potential for follow-up | Possible that follow-up will continue |  |
| Resources | Executive lead (Editor): 4 days/month Consultancy support: within 2009-2010 budget Project management: 2 days/month |  |

### Project name: Web programme (3/3) – Redesign of Cochrane.org and The Cochrane Library

| Description | Support web programme in the redesign of Cochrane.org and The Cochrane Library websites to improve visual presentation, internal navigation, and connectivity between the two sites |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | Harriet MacLehose and Toby Lasserson |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Introduce new home page and navigation for The Cochrane Library and cochrane.org |  |
| Interim steps | - Develop and consult on homepage design and navigation schemata - Prepare detailed specifications for the homepage redesigns - Outline and define the content that will be hosted on each site |  |
| Stakeholders | - Wiley-Blackwell - Freiburg Cochrane.org web team - Cochrane Library Users’ Group | - Information Management System team - Cochrane Review Groups |
| Total no. of months | 11-12 months |  |
| Start-finish date | November 2009 – October 2010 |  |
| Potential for follow-up | Possible that follow-up will continue, in particular aimed at improving web presentation and function at the level of the individual reviews. |  |
| Resources | Executive lead (Editor): 4 days/month Project management: 1 day/month |  |

### Project name: Updating programme

| Description | A complex programme of activities aimed at exploring the barriers to updating and providing and evaluating focussed centralised interventions with self-selected CRGs to improve performance in relation to prioritised reviews. This work will build on the work of, and engage with, other interested parties within the Collaboration. Consequently we will develop coherent, feasible, scoped proposals aimed at achieving the objective of all reviews being “fit for purpose” by end 2010. |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | Harriet MacLehose |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | 1. Diagnostic & Exploratory project: Identify barriers and facilitators to delivering updated reviews 2. Consultancy project: Support 4 to 6 CRGs in addressing backlog of reviews needing updating. Complete pilot project for self-selected CRGs: 12 months 3. Development plan Develop proposal for further work including outcomes and resources and present to CCSG – 12 months towards objectives stated above – all reviews fit for purpose by end 2012. |  |
| Interim steps | - Develop document to outline projects and refine with input from stakeholders; arrange a meeting with the Trials Search Co-ordinators’ Executive as part of this - Work with Canadian Cochrane Centre and the UK Cochrane Centre to agree proposals for pilot - Identify volunteer Cochrane Review Groups for pilot approaches - Consult with stakeholders and achieve consensus on way forwards at pilot and evaluation stages |  |
| Stakeholders | - Trials Search Co-ordinators’ Executive (on behalf of Trials Search Co-ordinators) - Executives of the Co-ordinating Editors and Managing Editors (on behalf of the Cochrane Review Groups) - Canadian Cochrane Centre | - UK Cochrane Centre - Co-chairs of the Cochrane Collaboration Steering Group - Editors of updating chapter of the Cochrane Handbook |
| Total no. of months | 12 months |  |
| Start–finish date | November 2009 – October 2010 |  |
| Potential for follow-up | Ongoing work is likely. |  |
| Resources | Executive lead (Editor): 15 days/month Information specialist: 5 days/month Project management: 1 day/month |  |

### Project name: Continuous publication record

| Description | To develop processes to enable continuous publication records for reviews to improve the experience for end users (eg in the CDSR and PubMed) and editorial staff (eg in Archie); and to redefine terminology in respect of withdrawn reviews and protocols. |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | Moderate |  |
| Executive lead | Harriet MacLehose |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - To explore the possibilities of modifying the publication process to permit the option for a new protocol as part of an update. - Improved cross-linking between related reviews (i.e. where a review has been split, lumped, or superseded) within Archie, CDSR and PubMed. - Withdrawn category replaced with defined actions for each of the reasons for withdrawal. |  |
| Interim steps | - Withdrawn: explore all reasons for withdrawing reviews, then create a number of defined actions for each reason, and see if the defined action could replace the need for the withdrawn category - Cross-linking records and option for a protocol: prepare a report based on feedback from the Singapore meeting, and arrange a meeting (virtual or in person) to detail specifications in time for the February 2010 IMS meeting |  |
| Stakeholders | - Executives for the Managing Editors, Co-ordinating Editors, and Trials Search Co-ordinators - Editorial Management Advisory Group - RevMan Advisory Group | - IMS team - Cochrane Review Groups - Wiley-Blackwell |
| Total no. of months | 11 months |  |
| Start–finish date | November 2009 – September 2010 |  |
| Potential for follow-up | Unlikely |  |
| Resources | Executive lead (Editor): 3 days/month Project management: 0.5 day/month |  |

### Project name: Publication ethics (1/3) – Publication of Cochrane Reviews in other journals

| Description | Clarification of Cochrane policy for publication of Cochrane Reviews in other journals or publications. |  |
| --- | --- | --- |
| Priority | Moderate |  |
| Urgency | Moderate |  |
| Executive lead | Harriet MacLehose |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Paper with worked-through proposals to Co-ordinating Editors’ Board meeting in April 2010. - Changes to Cochrane Policy Manual and Cochrane Handbook, if required. |  |
| Interim steps | - Draft policy documents. - Consultation with stakeholders and consensus building. |  |
| Stakeholders | - Executives (Co-ordinating Editors, Managing Editors, and Trials Search Co-ordinators) - Cochrane Review Groups - Cochrane Collaboration Steering Group Author representative (on behalf of authors) | - Publication Arbiters - Editors of the Cochrane Policy Manual and the Cochrane Handbook - Wiley-Blackwell - Diagnostic Test Accuracy Working Group |
| Total no. of months | 6 months |  |
| Start–finish date | November 2009 – April 2010 |  |
| Potential for follow-up | Ongoing maintenance and responses to queries |  |
| Resources | Executive lead (Editor): 2 days/month Project management: 0.5 day/month |  |

### Project name: Publication ethics (2/3) – Declaration of interests for authors and editors

| Description | To compare the new ICJME standard ‘disclosure of interest’ form with the Cochrane declaration of interest form, and explore options for adapting the ICJME form for use by Cochrane authors and Editors. |  |
| --- | --- | --- |
| Priority | Moderate |  |
| Urgency | Moderate |  |
| Executive lead | Harriet MacLehose |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Paper revised and presented to Co-ordinating Editors’ Board meeting in April 2010. - Changes to Cochrane Manual and Handbook, if required. - Policy change implemented by Cochrane Review Groups. |  |
| Interim steps | - Paper drafted and shared with the stakeholders for feedback on content and implications for implementation (before the Co-ordinating Editors’ Board meeting in April 2010). |  |
| Stakeholders | - Publishing Policy Group - Executives of the Co-ordinating Editors’ and Managing Editors’ (to represent the Cochrane Review Groups) - Funding Arbiter - Cochrane Collaboration Steering Group Author representative (on behalf of authors) | - Editors of the Cochrane Policy Manual and Cochrane Handbook (Interventions and Diagnostic) - Wiley-Blackwell (for legal input) - IMS team |
| Total no. of months | 10 months |  |
| Start–finish date | November 2009 – August 2010 |  |
| Potential for follow-up | Ongoing maintenance and responses to queries |  |
| Resources | Executive lead (Editor): 2 days/month Project management: 0.5 day/month |  |

### Project name: Publication ethics (3/3) – Plagiarism

| Description | To develop guidance on managing plagiarism, and to explore use of plagiarism detection software. |  |
| --- | --- | --- |
| Priority | Moderate |  |
| Urgency | Moderate |  |
| Executive lead | Harriet MacLehose |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Pilot of the CrossCheck plagiarism detection software is completed, and CrossCheck rolled-out to all Cochrane Review Groups if appropriate. - Summary paper presented to the Co-ordinating Editors’ Board meeting in April 2010. - Changes to Cochrane Policy Manual and Cochrane Handbooks (Intervention and Diagnostic), if required. |  |
| Interim steps | - CrossCheck pilot implemented and evaluated. - Guidance on managing plagiarism drafted based on CrossCheck experience and feedback from Cochrane Review Groups. - Consultation with stakeholders and consensus building. |  |
| Stakeholders | - Publishing Policy Group - Executives of the Co-ordinating Editors’ and Managing Editors’ (to represent the Cochrane Review Groups) - Publication Arbiters | - Editors of the Cochrane Policy Manual and Cochrane Handbook (Interventions and Diagnostic) - Wiley-Blackwell (for legal input) - IMS team |
| Total no. of months | 10 months |  |
| Start–finish date | November 2009 – August 2010 |  |
| Potential for follow-up | Likely to continue with roll-out of CrossCheck |  |
| Resources | Executive lead (Editor): 2 days/month Project management: 0.5 day/month |  |

### Project name: Copy-editing: Cochrane Style Guide and Copy Edit Support

| Description | To support the copy-editing group (Cochrane Style Guide Working Group and Copy Edit Support) to enhance and further develop copy-editing resources; and to implement a change in policy: all new or updated Cochrane Protocols and Reviews are copy-edited before publication either through Copy Edit Support or by an approved in-house CRG copy editor. |  |
| --- | --- | --- |
| Priority | Medium |  |
| Urgency | Medium |  |
| Executive lead | Harriet MacLehose (with Nancy Owens) |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Cochrane Style Guide up-to-date in response to user feedback and other Cochrane Collaboration developments (specifically, reviews of diagnostic test accuracy, overviews of reviews, and summary of findings tables) - All new Cochrane Protocols and Reviews copy-edited by (1) Copy Edit Support or (2) ‘approved’ in-house Cochrane Review Group copy editor - For Cochrane Review Group that do not use Copy Edit Support: in-house standards for copy-editing developed and agreed - Copy Edit Support: - Criteria developed and implemented for when a Cochrane Review is ready for copy-editing by Copy Edit Support - Process agreed by Co-ordinating Editors for Copy Edit Support to return Cochrane Reviews to editorial teams when problems in review methodology or content identified |  |
| Interim steps | - Cochrane Style Guide: collect and respond to user feedback. - Organize a meeting with Nancy Owens and the Cochrane Editorial Unit to discuss management of the copy-editing projects described. |  |
| Stakeholders | - Cochrane Review Groups (represented by the Executives of the Co-ordinating Editors, Managing Editors, and Trials Search Co-ordinators) - Publishing Policy Group | - Wiley-Blackwell - CRG Procedures Collection Working Group |
| Total no. of months | 12 months |  |
| Start–finish date | November 2009 – October 2010 |  |
| Potential for follow-up | Likely to continue |  |
| Resources | Executive lead (Editor): 2 days/month Project management: 1 day/month |  |

### Project name: Cochrane Register of Studies implementation

| Description | This project aims to support the preferred provider for the CRS RFP (Metaxis), and relevant stakeholders within the Collaboration to work together for a successful implementation of the Cochrane Register of Studies. |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | Harriet MacLehose |  |
| Project manager | Lucie Jones |  |
| Outcomes/outputs | Successful implementation of the CRS project |  |
| Interim steps | See contract document |  |
| Stakeholders | - Trials Search Co-ordinators - Wiley-Blackwell - End users of The Cochrane Library | - Metaxis - CRGs - Systematic reviewers outside the Collaboration. |
| Total no. of months | 18 months |  |
| Start–finish date | Jan 2010 - June 2011 |  |
| Potential for follow-up | Moderate – refinements to the register etc |  |
| Resources | Editorial support: unknown – 1-2 days/month Information specialist: 0.5 FTE (12 days / month) |  |

## 1.2. In development

### Project name: Implementing the Co-ordinating Editors’ endorsement of PRISMA

| Description | The Co-ordinating Editors endorsed the PRISMA statement at the 2009 Singapore Cochrane Colloquium. This impacts two specific areas for The Cochrane Collaboration: (1) the inclusion of the term “systematic review” in the Cochrane Review title; and (2) the inclusion of a study flowchart in each Cochrane Review. |  |
| --- | --- | --- |
| Priority | Moderate |  |
| Urgency | Moderate |  |
| Executive lead | Toby Lasserson |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - The term “systematic review” is included in the Cochrane Review title, preferably outside of CDSR but in the recommended CDSR citation - A study flowchart included in each new and updated Cochrane Review |  |
| Interim steps | - Liaison with IMS team and Wiley-Blackwell for the title project - Liaison with the RevMan Advisory Group, and the Executives of the Trials Search Co-ordinators and Managing Editors for the flowchart project |  |
| Stakeholders | - Trials Search Co-ordinators (represented by the Trials Search Co-ordinators’ Executive) - Authors (represented by the Cochrane Collaboration Steering Group Author representative) - IMS team | - Review Manager Advisory Group - Editorial teams (represented by the Managing Editors’ Executive) - Wiley-Blackwell - Publishing Policy Group |
| Total no. of months | 12 months |  |
| Start–finish date | November 2009 – October 2010 |  |
| Potential for follow-up | Limited |  |
| Resources | Executive lead (Editor): 2 days/month Project management: 0.5 day/month |  |

Project name: Supporting summary of findings table development

| Description | Summary of findings tables are a key deliverable to assist end users in making sense of the results of Cochrane reviews. We are aware that the CCSG has supported a training programme, but we propose to augment this from the CEU by organising and hosting webinar based training and one to on support, in support of the current programmes. |  |
| --- | --- | --- |
| Priority | Moderate |  |
| Urgency | Moderate |  |
| Executive lead | Toby Lasserson |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Regular programme of webinars - One to one support offered to CRGs and review authors - 50% increase in the number of new and updated reviews including competent summary of findings tables |  |
| Interim steps | - Organise training and ongoing supervision for CEU team |  |
| Stakeholders | - Authors | - Editorial teams - Wiley-Blackwell - Publishing Policy Group |
| Total no. of months | 12 months |  |
| Start–finish date | November 2009 – October 2010 |  |
| Potential for follow-up | Limited |  |
| Resources | Executive lead (Editor): 4 days/month Project management: 1 day/month |  |

# Appendix 2. Downstream product development

For each of these we present a table that includes a summary of the project, responsibilities, outcomes, resource utilization.

## 2.1. In progress

### Project name: Cochrane Response

| Description | Develop and evaluate a Cochrane Response brokerage service over next 12 to 15 months |
| --- | --- |
| Priority | High |
| Urgency | High |
| Executive lead | Harriet MacLehose and Toby Lasserson |
| Project manager | Giovanna Ceroni |
| Outcomes/outputs | - Collaboration-wide tender monitoring and alert system set-up - Four Cochrane Response projects completed - Evaluate Cochrane Response and present findings and recommendations to CCSG |
| Interim steps | - Develop scanning service for international evidence synthesis programmes and distribute to Cochrane Review Groups - Advertise Cochrane Response by developing ‘marketing strategy’ - Act as a broker and provide additional services as required in relation to commissioned reviews |
| Stakeholders | - Cochrane Review Groups - Cochrane Centres |
| Deadline | 17 months |
| Start–finish date | November 2009 – March 2011 |
| Potential for follow-up | Likely to continue |
| Resources | Executive lead (Editor): 6 days/month Project management: 2 days/month |

### Project name: Cochrane PICO

| Description | Complete pilot of Cochrane PICO and support user testing as required. |
| --- | --- |
| Priority | High |
| Urgency | High |
| Executive lead | Harriet MacLehose |
| Project manager | Giovanna Ceroni |
| Outcomes/outputs | - Complete 20 prototype Cochrane PICOs. - Assist evaluation of pilot and plans for onwards development for the Cochrane Collaboration Steering Group and Wiley approval. |
| Interim steps | - Prepare a Cochrane PICO template for use in the pilot. - Develop pilot, and identify and brief “authors”. - Revise template based on feedback during pilot. - Evaluate pilot. |
| Stakeholders | - Cochrane Review Groups - Wiley-Blackwell |
| Total no. of months | 7 months |
| Start–finish date | November 2009 – May 2010 |
| Potential for follow-up | Likely to continue with option to grow |
| Resources | Funding available £10,000 Executive lead (Editor): 9 days/month Project management: 2 days/month |

### Project name: Cochrane Education – Cochrane Journal Club

| Description | Support development of Cochrane Journal Club and ensure flow of high-quality content |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | Moderate |  |
| Executive lead | Toby Lasserson |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Cochrane Journal Club maintained, with new content posted every 6 weeks. |  |
| Interim steps | - Support Bryony Urquhart (Wiley-Blackwell) and Mike Clarke (Podcast Editor) to develop schedules for development and publication of Cochrane Journal Clubs. - Provide assistance in the content production and editing of final product. - Seek feedback from users and suggest changes based on their experiences |  |
| Stakeholders | - Podcast editor - Cochrane Review Groups | - Wiley-Blackwell - Cochrane web team |
| Total no. of months | 17 months |  |
| Start–finish date | November 2009 – March 2011 |  |
| Potential for follow-up | Likely to continue |  |
| Resources | Executive lead (Editor): 1 day/month Project management: 0.25 day/month |  |

## 2.2. In development / under consideration

### Project name: Cochrane Decision support

| Description | Work with InferMed, Duodecim, Wiley-Blackwell and other partners to create decision support offering based on CDSR content |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | David Tovey |  |
| Project manager | Harriet MacLehose |  |
| Outcomes/outputs | - Contractual agreement between CC and other partners - Successful pilot of decision support application in at one institution |  |
| Interim steps |  |  |
| Stakeholders | - Cochrane Collaboration Steering Group - Duodecim | - InferMed - Wiley-Blackwell |
| Total no. of months | Unknown at present |  |
| Start–finish date | Unknown |  |
| Potential for follow-up | High |  |
| Resources | Unknown |  |

### Project: Support for overviews

| Description | Work with other groups within Cochrane to determine methodological approach and accelerate progress |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | Moderate |  |
| Executive lead | David Tovey |  |
| Project manager | Harriet MacLehose |  |
| Outcomes/outputs | - Should aim for 200 overviews of reviews to cover major conditions |  |
| Interim steps | - Agree methodological approach and role of multiple comparison meta-analysis - Build capacity and support |  |
| Stakeholders | - Cochrane Collaboration Steering Group - CRGs | - Wiley-Blackwell |
| Total no. of months | Unknown at present |  |
| Start–finish date | Unknown |  |
| Potential for follow-up | High |  |
| Resources | Estimate about 20 days/ month editorial plus 1 day/month administrative support |  |

# Appendix 3. Projects: Collaboration development

For each of these we present a table that includes a summary of the project, responsibilities, outcomes, resource utilization.

## 3.1. In progress

### Project name: Consumer programme/mid-year meeting preparation

| Description | To work with consumers and other Collaboration entities and individuals towards the mid-year meeting (Auckland 2010) |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | David Tovey |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Preparatory document and worked through proposals for mid-year meeting - Development of action plan post mid-year meeting |  |
| Interim steps | - Provide administrative support to consumers |  |
| Stakeholders | - Co-Chairs - Consumers network | - Cochrane Review Groups |
| Total no. of months | 4-6 months |  |
| Start–finish date | November – March 2010 |  |
| Potential for follow-up | Moderate likelihood |  |
| Resources | Project management: 2 days/week |  |

### Project name: Editorial management of orphan Cochrane STD reviews

| Description | To act as the editorial base for review authors of six titles registered and in progress with the now deregistered Cochrane STD Group. This is an interim measure until a new editorial base is found for the STD Group. The Cochrane HIV/AIDS Group and the Cochrane Infectious Diseases Group are also providing temporary editorial management of specific titles. |  |
| --- | --- | --- |
| Priority | High |  |
| Urgency | High |  |
| Executive lead | Toby Lasserson |  |
| Project manager | Giovanna Ceroni |  |
| Outcomes/outputs | - Maintain protocols and reviews and organize support and editorial review of work until long-term status of STD Group is known. |  |
| Interim steps | - Provide editorial support (including help with search strategies and searching, and protocol and review development) to authors. |  |
| Stakeholders | - Reviews authors - Wiley-Blackwell | - IMS team |
| Total no. of months | 11 months |  |
| Start–finish date | November 2009 – September 2010 |  |
| Potential for follow-up | Unclear |  |
| Resources | Executive lead (Editor): 1 day/month Project management: 0.5 days/month Freelance Trials Search Coordinator: 6 days total (1 day/title) |  |