CORE FUNDING PROGRAMMES UPDATE: CCSG MEETING, AUCKLAND, 2010

| CURRENT RFP-FUNDED PROJECTS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Title of project | PI | Budget |  | ¤ | Principal Cochrane entity and contractual partner | Date Contract Signed and/or start date | Proposed end date | Notes |
| OPPORTUNITIES FUND 2007 (20070801) |  |  |  |  |  |  |  |  |
| Disseminating thousands of previously undiscovered trials | Clive Adams | 18,324 |  | GBP | Cochrane Schizophrenia Group | 10/09/2008 | c. April 2010 (due to agreed extension) | Extension granted due to delay in transferring funds |
| A portal to breast cancer clinical trials | Davina Ghersi | 25,000 |  | GBP | University of Sydney, on behalf of the Cochrane Breast Cancer Review Group | 16/04/2009 | April 2010 |  |
| Approaches to estimate and present baseline risks: recommendations for Cochrane review Summary of Findings (SoF) tables | Jill Hayden | 23,433 |  | GBP | Dalhousie University, on behalf of the Cochrane Back Review Group | 17/12/2008 | End of March 2010 |  |
| Making Cochrane information accessible to people in Nigeria | Martin Meremikwu | 22,375 |  | GBP | Nigerian Branch of the South African Cochrane Centre | 12/03/2009 | March 2010 |  |
| Continuing development and enhancement of the Cochrane Methodology Register | Mike Clarke | 21,095 |  | GBP | UKCC, on behalf of UKCC and Methodology Review Group | 01/11/08 | End of October 2009 | Final report in preparation. Project completed |
| OPPORTUNITIES FUND 2008 (20081708) |  |  |  |  |  |  |  |  |
| A Course for Cochrane Statisticians Addressing Advances in Meta-Analytical Techniques | Doug Altman | 16,500 |  | GBP | University of Oxford, on behalf of the Statistical Methods Group | 11/11/09 | November 2010 | Course to be held at UK and Ireland Cochrane Contributors’ meeting, 2-3 March 2010 |
| Evaluation of The Cochrane Collaboration’s Risk of Bias Tool | Jonathan Sterne | 29,354 |  | GBP | University of Bristol, on behalf of the Bias Methods Group | 30/09/09 | December 2010 |  |
| Cochrane Training: Developing a Core Collection of Approved Training And Support Materials | Steve McDonald | 48,997 |  | AUD | Monash University, on behalf of the Australasian Cochrane Centre | 02/11/09 | November 2009 |  |
| CURRENT CORE-FUNDED PROJECTS (OTHER) |  |  |  |  |  |  |  |  |
| DTAS (Australia): Extension Agreement: Register of reports of Diagnostic Test Accuracy Studies | Jonathan Craig | 77,830 | AUD |  | The Cochrane Renal Group | 13/11/2008 | October 2010 |  |
| CESU (Europe): Extension Agreement: Continental European Support Unit for Cochrane entities conducting Diagnostic Reviews of Test Accuracy | Rob Scholten | 49000 (+ 28,000 surplus) | EUR |  | Academisch Medisch Centrum, on behalf of the Dutch Cochrane Centre | 13/11/2008 | October 2010 |  |
| Chinese Randomised Controlled Trials Database | Mingming Zhang | 50,000 | GBP |  | West China Hospital, Sichuan University, on behalf of the Chinese Cochrane Centre | 22/06/2007 | c. October 2009 | Delay in project due to problems transferring funds to the Chinese Cochrane Centre. Project complete. Final report in preparation |
| Development and installation of the Cochrane Register of Studies | The CRS Project Board | 252,050 + VAT | GBP |  | The Cochrane Collaboration | 01/01/10 | June 2011 | Ongoing costs (server leasing, maintenance etc) will be in addition to the cost stated here |
| Training and capacity building for Summary of Findings (SoF) Tables | Holger Schünemann | 20,000 | GBP |  | Co-Eds Methods Working Group (contract with McMaster University) | 11/11/09 | February 2011 |  |

| RECENTLY COMPLETED RFP-FUNDED PROJECTS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OPPORTUNITIES FUND 2006 (20061101) |  |  |  |  |  |  |  |  |  |
| Developing and evaluating a plain language summary template for Cochrane Reviews | Claire Glenton | 16,954 | GBP |  | Nordic Cochrane Centre (Norwegian Branch) | 01/08/2007 | End May 2009 (following agreed extension) |  |  |
| RGC (now ME) induction and mentoring programme | Jessica Thomas | 16,100 | GBP |  | PaPaS | 19/07/2008 | End of December 2009 (due to agreed extension) |  | Unused funds being used to support ongoing ME mentoring programme as agreed by CCSG Exec |
| Making Cochrane Reviews more accessible to policy makers | John Lavis | 23,421 | GBP |  | McMaster University, on behalf of EPOC and the Canadian Cochrane Centre | 30/08/2007 | End of March 2008 |  | Project completed. Report outstanding. Unable to contact John Lavis |
| Web-based training for Cochrane review authors | Phil Wiffen | 17,070 | GBP |  | UK Cochrane Centre in collaboration with Portsmouth University | 29/08/2007 | End of April 2009 (following agreed extension) |  |  |
| Analytical methods to guide decisions of whether, and when, to update Cochrane Reviews | Sally Hopewell | 23,313 | GBP |  | UK Cochrane Centre | 24/07/2007 | End of July 2008 |  |  |
| OPPORTUNITIES FUND 2007 (20070801) |  |  |  |  |  |  |  |  |  |
| Beyond the database search: developing inclusive global registers of studies | Alison Weightman | 8,436 | GBP |  | Cardiff University, on behalf of the Cochrane Information Retrieval Methods Group | 15/10/2008 | October 2009 |  |  |
| PRIORITISATION FUND (20061102) |  |  |  |  |  |  |  |  |  |
| Piloting and evaluation of a patient-professional partnership approach to prioritising Cochrane Reviews and other research | Adrian Grant | 7,530 |  | GBP | The University of Aberdeen, on behalf The Cochrane Incontinence Review Group | 25/03/2008 | End of April 2009 (following agreed extension) |  |  |
| Prioritisation of Cochrane Reviews for consumers and the public in low and high-income countries as a way of promoting evidence-based healthcare | Janet Wale (10,000 Euros paid to Gerd Antes for work on project) | 18,100 |  | USD | Cochrane Consumer Network | 12/09/2007 | End of September 2008 |  |  |
| Using practice guidelines to determine review priorities: a pilot project | Kay Dickersin | 67,207 |  | USD | Johns Hopkins University, on behalf of the US Cochrane Centre | 12/10/2007 | October 2009 (following agreed extension) |  |  |
| Prioritizing Cochrane Review topics to reduce the know-do gap in low and middle income countries | Peter Tugwell | 17,194 |  | GBP | The University of Ottawa, on behalf of the Cochrane Health Equity Field | 19/07/2007 | May 2009 (following agreed extension) |  |  |
| Delivering on priorities: developing and implementing effective collaboration between a CRG and a Cochrane Field | Rajan Madhok (Helen Handoll) | 19,500 |  | GBP | The University of Manchester, on behalf of BJMT | 03/09/2007 | End of October 2009 (following agreed extension) |  |  |
| RECENTLY COMPLETED CORE-FUNDED PROJECTS (OTHER) |  |  |  |  |  |  |  |  |  |
| Interim funding to establish the Cochrane Sexually Transmitted Diseases (STD) Group in Porte Alegre, Brazil | Mauro Ramos | 43,900 | USD |  | Centro de Estudos de AIDS do Rio Grande do Sul (CEARGS) on behalf of the Cochrane STD Group, Brazil | 20/05/2008 |  | 19/05/2009 | Group deregistered. Final instalment not paid and returned to Cash Flow Forecast |
| Translation of Cochrane systematic reviews into Spanish | Xavier Bonfill | 60,000 | EUR |  | Iberoamerican Cochrane Centre | 06/02/2008 |  | 05/02/2010 |  |

NOTABLE UPDATES

FINAL REPORTS RECEIVED SINCE LAST UPDATE, SINGAPORE, 2009:

- Alison Weightman, Opportunities Fund

- Kay Dickersin, Prioritisation Fund

- Helen Handoll (Rajan Madhok), Prioritisation Fund

- Xavier Bonfill, Translation of Cochrane systematic reviews into Spanish

2010 ROUND OF THE OPPORTUNITIES FUND:

- Request for proposals (RFP) released: 18 December 2009

- Deadline for proposals: 26 February 2010

- Proposals recommended for funding submitted at this meeting (refer to paper in your agenda packs)

The improvements to the application process recommended by Donna Gillies at the Singapore meeting, which were approved by the CCSG at that meeting and refined at subsequent Exec teleconferences, were incorporated into the 2010 RFP and the servicing arrangements for Opportunities Fund Committee. Most notably, an application form was created, principally to standardise applications and to ensure applicants have the permission of their entities to apply (www.cochrane.org > A-Z Index > P > Project Application Form); and the majority of members of the Opportunities Fund Committee were chosen from outside the Steering Group by the entity executives:

- Chair: Donna Gillies

- Business oversight: Nick Royle

- CEU: David Tovey

- Consumer: Silvana Simi

- Co-Ed: Geraldine Macdonald

- Fields/Branches representative: Susan Wieland

- ME: Nicole Skoetz

- Methods representative: Ian Shemilt

- TSC: Samantha Roberts

THE FINAL REPORT FORM:

As agreed at the Singapore meeting, CCSG members commented on the format and content of the Final Report Form and amendments were made as suggested. A copy of the form is available on request.

THE PRIORITISATION FUND:

At the Colloquium in Singapore, a special session was conducted to examine the success of the Prioritisation Fund projects in the context of the strategic objectives of the Fund, and to explore the lessons to be learned for guiding future prioritisation efforts across the Collaboration. Chaired by Lisa Bero and David Tovey, the session included presentations by representatives from each of the projects and was themed around the issues identified in the strategic session at the CCSG’s 2006 mid-year meeting in Khon Kaen: whose priorities should Cochrane reviews address? What are the risks and benefits of prioritisation? Should we be using a ‘top-down’ or ‘bottom-up’ approach to prioritising reviews?

An article on the session was submitted to Cochrane News in November 2009, in which David commented: “What came across most strongly for me was the need for prioritisation to be a process that involves different groups of people working together, whether they are outside the Collaboration - as with patient groups or guidelines groups - or inside, as with fields and review groups. Otherwise the perspective is too narrow.”

Lisa also summarised her views: “I think we have learned that it would be difficult for The Cochrane Collaboration to have a single, top-down prioritisation scheme.  The projects showed us that different approaches can be used to identify priorities for different groups of people.  Although some of the approaches worked more smoothly than others, they were all relatively successful in identifying topics for high priority reviews.  However, the question of “whose priorities?” remains.  So, I think we have to encourage different prioritisation approaches and for the Collaboration as a whole to become more responsive in producing priority reviews for specific groups. The development of the special relationship between the Collaboration and the World Health Organization is a good example of how this can be achieved.

Lisa went on to say that: “One of the interesting new questions to come from the prioritisation session was whether reviews that have been produced as a result of a prioritisation process have more impact than non-prioritised reviews. We assume that priority reviews will be read, cited and will influence practice and policy, but we haven't actually measured that yet.”

The issues identified during the session, and the results of the projects themselves, are being taken forward in an article series, which is being coordinated by Mona Nasser, principal researcher on Peter Tugwell’s Prioritisation Fund project. Although this series will be published externally, there is a possibility that it could be used as a proto-type for themed articles series to be published in The Cochrane Library.

COCHRANE.ORG

The re-launch of cochrane.org is scheduled for mid-March 2010 and will represent a significant improvement in the management of the website’s content, which will make better access to the results and reports of projects possible. I will be working on this between the Auckland and Keystone meetings.

Lucie Jones

Cochrane Collaboration Secretariat

19 February 2010